## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Bagnan-I | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Bangalpur(Jl-43) (Part-E) | AE/Ulu |  | ORD/000817/2022-2023 | 1097/HD | 16/03/2023 | 15/04/2023 | JYOTY SOLAR POWER | 16.21 | 0 | 0 | 0
2 | HOWRAH | Bagnan-I | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Adra (Jl-44) (Part-A) | AE/Ulu |  | ORD/000812/2022-2023 | 1093/HD | 16/03/2023 | 15/04/2023 | SAIKAT ENTERPRISE | 11.88 | 0 | 0 | 0
3 | HOWRAH | Bagnan-I | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Joka(Jl-42) (Part-B) | AE/Ulu |  | ORD/000813/2022-2023 | 1094/HD | 16/03/2023 | 15/04/2023 | BHOLA NATH CONSTRUCTION | 11.78 | 0 | 0 | 0
4 | HOWRAH | Bagnan-I | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Bangalpur(Jl-43) (Part-D) | AE/Ulu |  | ORD/000816/2022-2023 | 1096/HD | 16/03/2023 | 15/04/2023 | AYUSH ENTERPRISE | 16.14 | 0 | 0 | 0
5 | HOWRAH | Bagnan-I | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Bangalpur(Jl-43) (Part-C) | AE/Ulu |  | ORD/000815/2022-2023 | 1095/HD | 16/03/2023 | 15/04/2023 | M/S BANERJEE ENGINEERING SYSTEM | 11.7 | 0 | 0 | 0
6 | HOWRAH | Bagnan-I | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1754/HD | 26/04/2023 | 26/04/2023 | Resource Division | 45.94 | 0 | 0 | 0
7 | HOWRAH | Bagnan-I | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Work Order for Preparation of DPR for new piped water supply scheme of Bangalpur PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE-USD | ORD/000446/2021-2022 | 247/HD | 07/02/2022 | 22/02/2022 | DULAL MAJUMDER | 3.1 | 0 | 0 | 100
8 | HOWRAH | Bagnan-I | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | 4864/HD | 22/11/2024 | 22/11/2024 | Resource Division | 7.39 | 0 | 0 | 0
9 | HOWRAH | Bagnan-I | Electrical | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Quotation for new service connection for Bangalpur w/s scheme, Ph No-I, in the district Howrah under Electrical Division, PHE Dte. ( SM/16760 ) Reference Id- 106680402, Application no- 1007951594 |  |  | BILL/01369/2024-2025 | 333 | 30/07/2024 | 30/07/2024 | WBSEDCL | 6.26 | 0 | 0 | 0
10 | HOWRAH | Bagnan-I | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bangalpur PWSS of Bagnan I Block Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/RWS/Bagnan I | ORD/000811/2022-2023 | 1091/HD | 16/03/2023 | 14/04/2025 | ZEOLITE FRESH INDIA | 52.14 | 0 | 0 | 30
11 | HOWRAH | Bagnan-I | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Work Order for Interconnection for 2nd TW and 1st Tube well (HW site) at Bangalpur Piped Water Supply scheme in Bagnan-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | je/blk/bagn1 | ORD/000818/2022-2023 | 1098/HD | 16/03/2023 | 17/11/2025 | SUNIL ENTERPRISE | 10.66 | 0 | 0 | 0
12 | HOWRAH | Bagnan-I | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia SubDivision, under Howrah Division P.H.E. Dte. (MouzaAdra (Jl-44)) (Part-A) and Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir with pipe connection and cost of pipes, specials with Soil test & Design for Augmentation of Bangalpur Piped Water Supply scheme of Bagnan-I Block under Howrah Division P.H.E. Dte. in the District of Howrah | AE/Ulu | JE/RWS/Bagnan I | ORD/000012/2023-2024 | 1592/HD | 12/04/2023 | 13/04/2026 | SUBHAS TRADING CO. | 368.95 | 0 | 0 | 46
13 | HOWRAH | Bagnan-I | Electrical | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bangalpur water supply scheme, T.W. No.- I, II & III, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000080/2023-2024 | 1997/ED | 19/05/2023 | 01/01/2026 | C.M.S. ENGINEERING CONCERN | 35.16 | 0 | 0 | 35
14 | HOWRAH | Bagnan-I | Howrah Division | Bangalpur Piped Water Supply Scheme with provision of FHTC, Block Bagnan-I, Howrah. | SM/16760 | New | Work Order for Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia SubDivision, under Howrah Division P.H.E. Dte. (Mouza Bangalpur(Jl-43) (Part-B) | AE/Ulu | je/blk/bagn1 | ORD/000883/2022-2023 | 1449/HD | 30/03/2023 | 27/05/2025 | DEV DAS SHAW | 192.05 | 0 | 0 | 19
Total | [13 empty] | 789.36 | 0 | 0