## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Uluberia-II | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 1754/HD | 26/04/2023 | 26/04/2023 | Resource Division | 44.93 | 0 | 0 | 0
2 | HOWRAH | Uluberia-II | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 4414/HD | 07/12/2023 | 07/12/2023 | Resource Division | 45.12 | 0 | 0 | 0
3 | HOWRAH | Uluberia-II | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 3396/HD | 21/09/2023 | 21/09/2023 | Resource Division | 48.32 | 0 | 0 | 0
4 | HOWRAH | Uluberia-II | Electrical | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Quotation Bill for New Service Connection at Kamina W/S. Sch. TW-II |  |  | BILL/04247/2023-2024 | 422 | 10/11/2023 | 10/11/2023 | WBSEDCL | 18 | 0 | 0 | 0
5 | HOWRAH | Uluberia-II | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Original quotation of WBSEDCL for Kamina Water Supply Scheme |  |  | BILL/00836/2023-2024 | BP-2023-24-485 | 23/11/2023 | 23/11/2023 | WBSEDCL | 22.69 | 0 | 0 | 0
6 | HOWRAH | Uluberia-II | Electrical | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kamina water supply scheme, T.W. No.- I & II, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000081/2023-2024 | 1998/ED | 19/05/2023 | 17/08/2023 | MENAKA ENTERPRISE | 22.87 | 0 | 0 | 40
7 | HOWRAH | Uluberia-II | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Work Order for Preparation of DPR for new piped water supply scheme of Kamina PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE-USD | ORD/000445/2021-2022 | 246/HD | 07/02/2022 | 22/02/2022 | DULAL MAJUMDER | 3.44 | 0 | 0 | 100
8 | HOWRAH | Uluberia-II | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 170/HD | 15/01/2024 | 15/01/2024 | Resource Division | 6.16 | 0 | 0 | 0
9 | HOWRAH | Uluberia-II | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Work Order for Sinking of 7 (Seven) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Bamunhati PWSS (3 nos) & Kamina PWSS (2 nos) & Barramnagar PWSS (2 nos) of Uluberia - II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000881/2022-2023 | 1195/HD | 23/03/2023 | 17/07/2025 | ACME CONSTRUCTION | 90.87 | 0 | 0 | 85
10 | HOWRAH | Uluberia-II | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Work Order for Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials for in Kamina PWSS of Uluberia-II Block under Uluberia Sub Division under Howrah Division P.H.E. Dte. in the District of Howrah. | AE/Ulu | JE-USD | ORD/000010/2023-2024 | 1593/HD | 12/04/2023 | 28/09/2025 | ARUP NANDY | 138.34 | 0 | 0 | 90
11 | HOWRAH | Uluberia-II | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Kamina PWSS of Uluberia-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-A) | AE/Ulu | JE-USD | ORD/000025/2023-2024 | 1690/HD | 20/04/2023 | 10/04/2025 | JAHANGIR ALAM | 263.67 | 0 | 0 | 100
12 | HOWRAH | Uluberia-II | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Kamina PWSS of Uluberia-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-B) | AE/Ulu | JE-USD | ORD/000858/2022-2023 | 1190/HD | 23/03/2023 | 07/05/2023 | M/S ANUBHAB CONSTRUCTION | 92.63 | 0 | 0 | 100
13 | HOWRAH | Uluberia-II | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 19/03/2025 | TECH VISION | 12.48 | 0 | 0 | 62
14 | HOWRAH | Uluberia-II | Howrah Division | Kamina Piped Water Supply Scheme with provision of FHTC | SM/16927 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Kamina PWSS of Uluberia-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-C) | AE/Ulu | JE-USD | ORD/000859/2022-2023 | 1191/HD | 23/03/2023 | 19/04/2025 | SUSHANTA MONDAL | 27.98 | 0 | 0 | 100
Total | [13 empty] | 837.5 | 0 | 0