## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 8.7 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Keshabpur PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000231/2022-2023 | 84/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.64 | 3.64 | 100 | 100
3 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 4718/HD | 27/12/2023 | 27/12/2023 | Resource Division | 88.18 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Work Order for Construction of Boundary Wall, Repairing of Pump House (3.60 m x 3.00 m), Laying of Distribution Pipeline & Providing FHTC (1413 nos) for Augmentation of Keshabpur PWSS of Domjur Block under Howrah Division, PHE Dte. (Part-II) | AE/SADAR | JE/BLK/DOM/HOW,je1_iu,je_blk_ballyjag_how | ORD/000016/2023-2024 | 1547/HD | 04/04/2023 | 03/06/2023 | MA MANASA CONSTRUCTION | 152.7 | 19.13 | 12.53 | 20
5 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Keshabpur PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE/BLK/DOM/HOW,je1_iu,je_blk_ballyjag_how | ORD/000003/2023-2024 | 1529/HD | 04/04/2023 | 08/05/2025 | GARHBETA-I UNEMPLOYED YOUTH ENGINEERS CO OP | 25.31 | 0 | 0 | 100
6 | HOWRAH |  | Electrical | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Keshabpur water supply scheme, T.W. No. I, II & III, Block: Domjur, District - Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001358/2023-2024 | 4694/ED | 08/12/2023 | 01/07/2025 | DAS ENTERPRISE | 32.91 | 0 | 0 | 40
7 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Laying of additional distribution pipe line and Road restoration at Keshabpur PWSS at Domjur Block under Howrah Sadar Sub-Division of Howrah Division PHE. | AE/SADAR |  | ORD/000645/2024-2025 | 1250/HD | 06/03/2025 | 05/05/2025 | MA MANASA CONSTRUCTION | 27.71 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Construction of Pump House (5.40m x 3.60m) at 1st Tube Well Site, Laying of Rising main from Tube well including Road restoration & specials, Laying of Distribution system & providing Functional Household Tap Connection (FHTC) for Augmentation of KESHABPUR PWSS at Domjur Block under Howrah Division P.H.E Dte. (PART-1) [No. of FHTC = 1413] | AE/SADAR | je1_iu,je_blk_ballyjag_how | ORD/000454/2023-2024 | 217/HD | 17/01/2024 | 10/07/2025 | UNIQUE AGENCY | 194 | 0 | 0 | 10
Total | [13 empty] | 533.16 | 22.77 | 4.27