## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 8.7 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Keshabpur PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000231/2022-2023 | 84/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 3.64 | 3.64 | 100 | 100
3 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 4718/HD | 27/12/2023 | 27/12/2023 | Resource Division | 88.18 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Work Order for Construction of Boundary Wall, Repairing of Pump House (3.60 m x 3.00 m), Laying of Distribution Pipeline & Providing FHTC (1413 nos) for Augmentation of Keshabpur PWSS of Domjur Block under Howrah Division, PHE Dte. (Part-II) | AE/SADAR | JE/BLK/DOM/HOW,je1_iu,je_blk_ballyjag_how | ORD/000016/2023-2024 | 1547/HD | 04/04/2023 | 03/06/2023 | MA MANASA CONSTRUCTION | 152.7 | 90.49 | 59.26 | 20
5 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Keshabpur PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE/BLK/DOM/HOW,je1_iu,je_blk_ballyjag_how | ORD/000003/2023-2024 | 1529/HD | 04/04/2023 | 08/05/2025 | GARHBETA-I UNEMPLOYED YOUTH ENGINEERS CO OP | 25.31 | 0 | 0 | 100
6 | HOWRAH |  | Electrical | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Keshabpur water supply scheme, T.W. No. I, II & III, Block: Domjur, District - Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001358/2023-2024 | 4694/ED | 08/12/2023 | 01/07/2025 | DAS ENTERPRISE | 32.91 | 0 | 0 | 40
7 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Laying of additional distribution pipe line and Road restoration at Keshabpur PWSS at Domjur Block under Howrah Sadar Sub-Division of Howrah Division PHE. | AE/SADAR |  | ORD/000645/2024-2025 | 1250/HD | 06/03/2025 | 05/05/2025 | MA MANASA CONSTRUCTION | 27.71 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Construction of Pump House (5.40m x 3.60m) at 1st Tube Well Site, Laying of Rising main from Tube well including Road restoration & specials, Laying of Distribution system & providing Functional Household Tap Connection (FHTC) for Augmentation of KESHABPUR PWSS at Domjur Block under Howrah Division P.H.E Dte. (PART-1) [No. of FHTC = 1413] | AE/SADAR | je1_iu,je_blk_ballyjag_how | ORD/000454/2023-2024 | 217/HD | 17/01/2024 | 10/07/2025 | UNIQUE AGENCY | 194 | 66.24 | 34.14 | 10
9 | HOWRAH |  | Howrah Division | Augmentation of Keshabpur Water supply scheme | SM/16947 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Piped Water Supply Schemes in different Blocks in the District of Howrah under Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000111/2024-2025 | 3730/HD | 29/08/2024 | 28/09/2024 | HORIZEN | 4.93 | 0 | 0 | 100
Total | [13 empty] | 538.09 | 160.37 | 29.8