## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Material Requisition To Resource Division |  |  | RTOR000060/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 22.24 | 0 | 0 | 0
2 | HOWRAH | Domjur | Electrical | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-II) Uttar Jhapardaha water supply scheme, T.W. No. I, II, III & IV, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000057/2023-2024 | 1801/ED | 24/04/2023 | 23/07/2023 | DEY ENTERPRISE | 42.99 | 0 | 0 | 0
3 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 163.76 | 0 | 0 | 0
4 | HOWRAH | Domjur | Electrical | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Quotation Bill for New Service Connection at Uttar Jhapordah W/S. Sch. Z-II, PH-I |  |  | BILL/04325/2023-2024 | 438 | 23/11/2023 | 23/11/2023 | WBSEDCL | 3.72 | 0 | 0 | 0
5 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Work Order for Construction of 4 Nos Pump House (5.40m x 3.60m) at 1st 2nd,3rd &4th Tube Well Site, Construction of Boundary Wall at 1st Tube Well Site, 3 nos Boundary Wall at 2nd , 3rd & 4th Tube Well SiteConstruction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Rising Main Pipeline Work From 3rd Pump House, 2nd Pump House to 1st Pump House & OHR, Laying Distribution of Pipeline & Providing FHTC (Functional Household Tap Connection) for Augmentation of Domjur (Zone-II) Uttar Jhapardaha PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,je_blk_ballyjag_how,JE Sadar | ORD/000044/2023-2024 | 1831/HD | 02/05/2023 | 24/06/2025 | PRAVAT SARKAR | 607.14 | 233.33 | 38.43 | 10
6 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Work Order for Sinking of 7 (Seven) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone 1) Mahisnala PWSS & Domjur (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000001/2023-2024 | 1530/HD | 04/04/2023 | 19/05/2023 | BALAJI UDDYOG | 89.53 | 0 | 0 | 70
7 | HOWRAH | Domjur | Electrical | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Quotation money deposition for new service connection at Uttar Jhapordah pwss, T.W No.-I , Dist-Howrah under ED PHED. App. No.-1007533769 Ref. ID.: 106472906 SM/17175 |  |  | BILL/06203/2023-2024 | 813 | 28/02/2024 | 28/02/2024 | WBSEDCL | 6.94 | 0 | 0 | 0
8 | HOWRAH | Domjur | Electrical | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Quotation money deposition for new service connection at UTTAR JHAPORDAH pwss, T.W No.-III Dist-Howrah, under PHED. App. No.-1007553536 Ref. ID.-106486515 SM/17175 |  |  | BILL/06211/2023-2024 | 816 | 01/03/2024 | 01/03/2024 | WBSEDCL | 15.45 | 0 | 0 | 0
9 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Land Development Works of Uttar Jhapardaha (Zone-2) PWSS 1st, 2nd, 3rd & 4th Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR |  | ORD/000447/2024-2025 | 975/HD | 19/02/2025 | 05/04/2025 | SONAR BANGLA ENTERPRISE | 15.11 | 0 | 0 | 0
Total | [13 empty] | 966.88 | 233.33 | 24.13