## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Material Requisition To Resource Division |  |  | RTOR000060/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 22.24 | 0 | 0 | 0
2 | HOWRAH | Domjur | Electrical | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-II) Uttar Jhapardaha water supply scheme, T.W. No. I, II, III & IV, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000057/2023-2024 | 1801/ED | 24/04/2023 | 23/07/2023 | DEY ENTERPRISE | 42.99 | 0 | 0 | 0
3 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 1748/HD | 25/04/2023 | 25/04/2023 | Resource Division | 163.76 | 0 | 0 | 0
4 | HOWRAH | Domjur | Electrical | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Quotation Bill for New Service Connection at Uttar Jhapordah W/S. Sch. Z-II, PH-I |  |  | BILL/04325/2023-2024 | 438 | 23/11/2023 | 23/11/2023 | WBSEDCL | 3.72 | 0 | 0 | 0
5 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Work Order for Construction of 4 Nos Pump House (5.40m x 3.60m) at 1st 2nd,3rd &4th Tube Well Site, Construction of Boundary Wall at 1st Tube Well Site, 3 nos Boundary Wall at 2nd , 3rd & 4th Tube Well SiteConstruction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Rising Main Pipeline Work From 3rd Pump House, 2nd Pump House to 1st Pump House & OHR, Laying Distribution of Pipeline & Providing FHTC (Functional Household Tap Connection) for Augmentation of Domjur (Zone-II) Uttar Jhapardaha PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,je_blk_ballyjag_how,JE Sadar | ORD/000044/2023-2024 | 1831/HD | 02/05/2023 | 24/06/2025 | PRAVAT SARKAR | 607.14 | 233.33 | 38.43 | 10
6 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Work Order for Sinking of 7 (Seven) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone 1) Mahisnala PWSS & Domjur (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000001/2023-2024 | 1530/HD | 04/04/2023 | 19/05/2023 | BALAJI UDDYOG | 89.53 | 0 | 0 | 70
7 | HOWRAH | Domjur | Electrical | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Quotation money deposition for new service connection at Uttar Jhapordah pwss, T.W No.-I , Dist-Howrah under ED PHED. App. No.-1007533769 Ref. ID.: 106472906 SM/17175 |  |  | BILL/06203/2023-2024 | 813 | 28/02/2024 | 28/02/2024 | WBSEDCL | 6.94 | 0 | 0 | 0
8 | HOWRAH | Domjur | Electrical | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Quotation money deposition for new service connection at UTTAR JHAPORDAH pwss, T.W No.-III Dist-Howrah, under PHED. App. No.-1007553536 Ref. ID.-106486515 SM/17175 |  |  | BILL/06211/2023-2024 | 816 | 01/03/2024 | 01/03/2024 | WBSEDCL | 15.45 | 0 | 0 | 0
9 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Land Development Works of Uttar Jhapardaha (Zone-2) PWSS 1st, 2nd, 3rd & 4th Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR |  | ORD/000447/2024-2025 | 975/HD | 19/02/2025 | 05/04/2025 | SONAR BANGLA ENTERPRISE | 15.11 | 0 | 0 | 0
10 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Pernamnent restoration of damaged pavement caused by laying of Public Helath Engineering Directorate's pipe line for the PMGSY Road 57A Bus stand to Narna more of Domjur Block, Howrah under WBSRDA HOwrah Division -I (Package No. WB-09-01) under Domjur Zone - II Uttar Jhapardaha PWSS (SM Code - SM/17175) |  |  | BILL/00762/2025-2026 |  | 12/09/2025 | 12/09/2025 | WBSRDA-I | 20.05 | 0 | 0 | 0
11 | HOWRAH | Domjur | Howrah Division | Domjur (Zone-II) Uttar Jhapardaha PWSS with provision of FHTC Connection, Block- Domjur, District-Howrah. | SM/17175 | New | Supplying,fitting,fixing and erecting of Display Board at Domjur (Zone -II) Uttar Jhapardaha PWSS [SM/17175], Baniara PWSS [SM/11722], Makardaha PWSS [SM/11159] of Domjur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/000973/2024-2025 | 222-A/HSSD | 25/02/2025 | 12/03/2025 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
Total | [13 empty] | 987.79 | 233.33 | 23.62