## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Panchla | Electrical | Dakshin Panchla Piped Water Supply Scheme | SM/17196 | New | upply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dakshin Panchla water supply scheme, T.W. No. I & II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000045/2023-2024 | 1731/ED | 19/04/2023 | 18/07/2023 | SANKAR PRASAD DUTTA & CO. | 10.91 | 0 | 0 | 0
2 | HOWRAH | Panchla | Howrah Division | Dakshin Panchla Piped Water Supply Scheme | SM/17196 | New | Work Order for Construction of 100 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/6/2012) including Soil Investigation, Foundation Design & All pipe Connection, Pump House (5.40m x 3.60 m), Construction of Boundary Wall at Head work Site, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work ,Providing FHTC (Functional Household Tap Connection) for Dakshin Panchla PWSS at Panchla Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000031/2023-2024 | 1735/HD | 25/04/2023 | 25/03/2024 | BISWAJIT BAG | 180.62 | 0 | 0 | 0
3 | HOWRAH | Panchla | Electrical | Dakshin Panchla Piped Water Supply Scheme | SM/17196 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dakshin Panchla water supply scheme, T.W. No. II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000874/2023-2024 | 3447/ED | 11/08/2023 | 09/11/2023 | BARISAL TRADING CO. | 10.74 | 0 | 0 | 0
4 | HOWRAH | Panchla | Howrah Division | Dakshin Panchla Piped Water Supply Scheme | SM/17196 | New | Continuation order for Preparation of DPR for augmentation of existing piped water supply scheme of Dakshin Panchla PWSS, Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR |  | ORD/000979/2022-2023 | 1460/HD | 14/07/2022 | 13/08/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.63 | 0 | 0 | 100
5 | HOWRAH | Panchla | Howrah Division | Dakshin Panchla Piped Water Supply Scheme | SM/17196 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 135/HD | 10/01/2024 | 10/01/2024 | Resource Division | 4.98 | 0 | 0 | 0
6 | HOWRAH | Panchla | Howrah Division | Dakshin Panchla Piped Water Supply Scheme | SM/17196 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Dakshin Panchla PWSS of Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000002/2023-2024 | 1528/HD | 04/04/2023 | 06/08/2025 | ZEOLITE FRESH INDIA | 25.71 | 0 | 0 | 100
Total | [13 empty] | 235.59 | 0 | 0