## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta-I | Howrah Division | Ghuteghari Piped Water Supply Scheme | SM/17198 | New | Continuation order for r Preparation of DPR for new piped water supply scheme of Ghutegari PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu |  | ORD/001022/2022-2023 | 1508/HD | 21/07/2022 | 05/08/2022 | APEX ENGINEERING | 3.17 | 0 | 0 | 0
2 | HOWRAH | Amta-I | Electrical | Ghuteghari Piped Water Supply Scheme | SM/17198 | New | Quotation for new connection of Ghuteghari water supply scheme (Mini), Amta-I, Howrah Application No. 5004019125 Reference id: 503565825 SM/17198 UNDER JANGIPARA CCC, HOOGHLY |  |  | BILL/06260/2023-2024 | 858 | 11/03/2024 | 11/03/2024 | WBSEDCL | 0.3 | 0 | 0 | 0
3 | HOWRAH | Amta-I | Howrah Division | Ghuteghari Piped Water Supply Scheme | SM/17198 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 17/02/2025 | TECH VISION | 12.67 | 0.06 | 0.5 | 100
Total | [13 empty] | 16.13 | 0.06 | 0.39