## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta - I | Howrah Division | Ghuteghari Piped Water Supply Scheme | SM/17198 | New | Work Order for Sinking of 1 (One) No. Tubewell (150mmx100mm), Construction of Switch Room (3750mmx3750mm) & Laying Distribution System for providing Functional House hold Tap Connection (FHTC) at Ghutegari Mini PWSS under Amta-I Block under Uluberia Sub- Division under Howrah Division PHE Dte. | AE/Ulu | JE/BLK/amta1 | ORD/000007/2023-2024 | 1534/HD | 04/04/2023 | 03/07/2023 | M/S AHAMED CONSTRUCTION | 27.24 | 0 | 0 | 0
2 | HOWRAH | Amta - I | Howrah Division | Ghuteghari Piped Water Supply Scheme | SM/17198 | New | Continuation order for r Preparation of DPR for new piped water supply scheme of Ghutegari PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu |  | ORD/001022/2022-2023 | 1508/HD | 21/07/2022 | 05/08/2022 | APEX ENGINEERING | 3.17 | 0 | 0 | 0
3 | HOWRAH | Amta - I | Electrical | Ghuteghari Piped Water Supply Scheme | SM/17198 | New | Quotation for new connection of Ghuteghari water supply scheme (Mini), Amta-I, Howrah Application No. 5004019125 Reference id: 503565825 SM/17198 UNDER JANGIPARA CCC, HOOGHLY |  |  | BILL/06260/2023-2024 | 858 | 11/03/2024 |  | WBSEDCL | 0.3 | 0 | 0 | null
4 | HOWRAH | Amta - I | Electrical | Ghuteghari Piped Water Supply Scheme | SM/17198 | New | Quotation for new connection of Ghuteghari water supply scheme (Mini), Amta-I, Howrah Application No. 5004019125 Reference id: 503565825 SM/17198 UNDER JANGIPARA CCC, HOOGHLY |  |  | BILL/06260/2023-2024 | 858 | 11/03/2024 |  | WBSEDCL | 0.3 | 0 | 0 | null
Total | [13 empty] | 31 | 0 | 0