## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta-II | Howrah Division | Shibgachhia Piped Water Supply Scheme | SM/18193 | New | Preparation of DPR for new piped water supply scheme of Shibgachia PWSS, Amta-II Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000360/2022-2023 | 455/AE/USD | 15/09/2022 | 30/10/2022 | VOYAGER | 3.2 | 2.72 | 84.87 | 0
2 | HOWRAH | Amta-II | Howrah Division | Shibgachhia Piped Water Supply Scheme | SM/18193 | New | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 4184/HD | 22/11/2023 | 22/11/2023 | Resource Division | 23.18 | 0 | 0 | 0
3 | HOWRAH | Amta-II | Electrical | Shibgachhia Piped Water Supply Scheme | SM/18193 | New | Quotation Bill for New Service Connection at Sibgachia W/S. Sch. |  |  | BILL/04504/2023-2024 | 550 | 21/12/2023 | 21/12/2023 | WBSEDCL | 5.62 | 0 | 0 | 0
4 | HOWRAH | Amta-II | Electrical | Shibgachhia Piped Water Supply Scheme | SM/18193 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Shibgachhia water supply scheme, T.W. No. I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/003466/2023-2024 | 1909/ED | 12/05/2023 | 10/08/2023 | A.G. ENTERPRISE | 20.49 | 9.96 | 48.6 | 50
5 | HOWRAH | Amta-II | Howrah Division | Shibgachhia Piped Water Supply Scheme | SM/18193 | New | Display Board at different PWSS at Amta-II Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000645/2023-2024 | 3220/AE/USD | 12/03/2024 | 11/04/2024 | ABONTICA ENTERPRISE | 4.76 | 4.76 | 100 | 100
6 | HOWRAH | Amta-II | Howrah Division | Shibgachhia Piped Water Supply Scheme | SM/18193 | New | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 170/HD | 15/01/2024 | 15/01/2024 | Resource Division | 2.4 | 0 | 0 | 0
7 | HOWRAH | Amta-II | Electrical | Shibgachhia Piped Water Supply Scheme | SM/18193 | New | Quotation for new service connection for Shibgachchia water supply scheme, Tubewell No. II, Block: Amta-II, Howrah SM/18193 Application No. 1007523518 Reference id: 106465462 |  |  | BILL/06054/2023-2024 | 756 | 16/02/2024 | 16/02/2024 | WBSEDCL | 7.89 | 0 | 0 | 0
8 | HOWRAH | Amta-II | Howrah Division | Shibgachhia Piped Water Supply Scheme | SM/18193 | New | Sinking of 2 nos Tube Well, Laying Distribution System & Construction of 100 cum RCC OHR & Interconnection between Tubewells & OHR for SHIBGACHHIA PWSS OF AMTA-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE | AE/Ulu | JE/USD | ORD/000130/2023-2024 | 2646/HD | 18/07/2023 | 19/04/2026 | MITHU BUILDERS | 262.08 | 126.66 | 48.33 | 70
9 | HOWRAH | Amta-II | Howrah Division | Shibgachhia Piped Water Supply Scheme | SM/18193 | New | Construction of 2nos switch room (5.40m x 3.60m) with water supply & sanitary arrangement at Head Work site & 2nd TW site of Shibgachia PWSS [SM/18193] of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000309/2023-2024 | 4340/HD | 04/12/2023 | 24/09/2025 | KALIDAS ENTERPRISE | 12.56 | 6.1 | 48.53 | 100
10 | HOWRAH | Amta-II | Howrah Division | Shibgachhia Piped Water Supply Scheme | SM/18193 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 17/02/2025 | TECH VISION | 12.67 | 0.67 | 5.28 | 100
Total | [13 empty] | 354.86 | 150.86 | 42.51