## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Preparation of DPR for Augmentation of Udaynarayanpur (Zone-I) PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000252/2022-2023 | 326/AE/USD | 16/08/2022 | 30/09/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.2 | 3.19 | 99.56 | 100
2 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Preparation of DPR for Augmentation of Udaynarayanpur (Zone-II) PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000253/2022-2023 | 327/AE/USD | 16/08/2022 | 30/09/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.18 | 4.18 | 99.83 | 100
3 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 421/HD | 03/02/2023 | 03/02/2023 | Resource Division | 70.86 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 2830/HD | 04/08/2023 | 04/08/2023 | Resource Division | 49.53 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Construction of Boundary Wall, Construction of Approach Road and Land Development and Additional Laying of Distribution Pipe Lines with providing FHTC for leftout area for UDAYNARAYANPUR ZONE-I of UDAYNARAYANPUR ZONE-I & II Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. (SM/18398) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000039/2024-2025 | 2861/HD | 24/06/2024 | 23/08/2024 | M/S B.S.P. ENTERPRISES | 171.67 | 24.1 | 14.04 | 40
6 | HOWRAH |  | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF UDAYNARAYANPUR PIPED W/S SCHEME, Zone - I & II, T.W. No. III, District - Howrah under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002509/2023-2024 | 425/ED | 29/02/2024 | 29/05/2024 | PERFECT AIRCONDITION | 10.75 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Udaynarayanpur PWSS Zone -I (2 nos) and Zone-II (1 no) of Augmentation Udaynarayanpur Block Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000260/2023-2024 | 3618/HD | 09/10/2023 | 23/11/2023 | MUNSHI ENTERPRISE | 52.12 | 43.76 | 83.95 | 90
8 | HOWRAH |  | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Udaynarayanpur water supply scheme, Zone- I, T.W. No. III, Dist.- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001624/2021-2022 | 539/HMSD | 17/03/2022 | 07/04/2022 | C.M. ENTERPRISE | 2.74 | 2.72 | 99.43 | 90
9 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at different PWSS of Udaynarayanpur Block under Howrah R.W.S Sub-Division, under Howrah Division, P.H.E. Dte.(Part-D) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000752/2023-2024 | 85/RWS | 08/02/2024 | 23/02/2024 | ABONTICA ENTERPRISE | 0.57 | 0.57 | 100 | 80
10 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at different PWSS of Udaynarayanpur Block under Howrah R.W.S Sub-Division, under Howrah Division, P.H.E. Dte. (Part-C) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000751/2023-2024 | 84/RWS | 08/02/2024 | 23/02/2024 | ABONTICA ENTERPRISE | 0.91 | 0.91 | 100 | 80
11 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at different PWSS of Udaynarayanpur Block under Howrah R.W.S Sub-Division, under Howrah Division, P.H.E. Dte.(Part-B) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000750/2023-2024 | 83/RWS | 08/02/2024 | 23/02/2024 | ABONTICA ENTERPRISE | 0.91 | 0.91 | 100 | 80
12 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at different PWSS of Udaynarayanpur Block under Howrah R.W.S Sub-Division, under Howrah Division, P.H.E. Dte.(part-A) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000749/2023-2024 | 82/RWS | 08/02/2024 | 23/02/2024 | ABONTICA ENTERPRISE | 0.91 | 0.91 | 100 | 80
13 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 1049/HD | 04/03/2024 | 04/03/2024 | Resource Division | 132.58 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Permanent restoration work of probable damage stretches of Udaynarayanpur-Pancharul road, from ch. 0.00 km to 0.50 km & Amta-Rajapur-Dihibhurshut road from 15.50 km to 16.20 km, due to laying of water supply pipe line by P.H.E. i.c.w. rejuvenation of Udaynarayanpur water supply project under Howrah highway division, P.W.(Roads) Dte. in the district of Howrah. |  |  | BILL/00396/2024-2025 | BP-2024-25-241 | 06/08/2024 | 06/08/2024 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 6.65 | 0 | 0 | 0
15 | HOWRAH |  | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Quotation for new service connection for Augmentation of Udaynaraynpur Zone-I & II Water Supply Scheme, PH NO- II in the district Howrah under Electrical Division, PHE Dte. ( SM/18398), Reference Id- 106420105, Application no- 1007452865 |  |  | BILL/06588/2023-2024 | 910 | 21/03/2024 | 21/03/2024 | WBSEDCL | 3.9 | 0 | 0 | 0
16 | HOWRAH |  | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Quotation for new service connection for source Augmentation of Udaynarayanpur Water Supply Scheme, Zone- I & II, TW NO- III in the district Howrah under Electrical Division, PHE Dte. (SM/18398), Reference Id- 106743785 Application no- 1008083381 |  |  | BILL/02060/2024-2025 |  | 03/10/2024 | 03/10/2024 | WBSEDCL | 7.68 | 0 | 0 | 0
17 | HOWRAH |  | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Quotation for new service connection for source Augmentation of Udaynarayanpur Water Supply Scheme, Zone- I & II, TW NO- III in the district Howrah under Electrical Division, PHE Dte. (SM/18398), Reference Id- 106743785 Application no- 1008083381 |  |  | BILL/02834/2024-2025 | 498 | 21/10/2024 | 21/10/2024 | WBSEDCL | 6.9 | 0 | 0 | 0
18 | HOWRAH |  | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of MARCH,2024 |  |  | BILL/00827/2024-2025 | 225 | 18/06/2024 | 18/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.16 | 0 | 0 | 0
19 | HOWRAH |  | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of April,2024 |  |  | BILL/00828/2024-2025 | 227 | 18/06/2024 | 18/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.2 | 0 | 0 | 0
20 | HOWRAH |  | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Quotation for new service connection for Augmentation of Udaynaraynpur Zone-I & II Water Supply Scheme, PH NO- I in the district Howrah under Electrical Division, PHE Dte. ( SM/18398), Reference Id- 106420083, Application no- 1007452782 |  |  | BILL/06587/2023-2024 | 912 | 21/03/2024 | 21/03/2024 | WBSEDCL | 3.14 | 0 | 0 | 0
21 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | NDT for OHR of Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme |  |  | BILL/00329/2024-2025 | BP-2024-25-216 | 26/07/2024 | 26/07/2024 | JADAVPUR UNIVERSITY | 1.77 | 0 | 0 | 0
22 | HOWRAH |  | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of February,2024 |  |  | BILL/00826/2024-2025 | 224 | 18/06/2024 | 18/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.2 | 0 | 0 | 0
23 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) and construction of 2 nos Pump House (H/W Site & 2nd T/W Site) for UDAYNARAYANPUR Agumentation Zone-I Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000129/2023-2024 | 2645/HD | 18/07/2023 | 22/03/2026 | M/S B.S.P. ENTERPRISES | 378.71 | 325.97 | 86.07 | 75
24 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) & construction of 750 cum capacity 20mtr staging height RCC Over head Reservoir (including pile foundation), pipe connection & cost of pipes & soil investigation with design for pile foundation & construction of 1no Pump house at HW site for Udaynarayanpur Augmentation Zone-II Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000138/2023-2024 | 2759/HD | 31/07/2023 | 15/01/2026 | GHOSH CONCERN | 723.52 | 371.6 | 51.36 | 30
25 | HOWRAH |  | Electrical | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Udaynarayanpur (Zone-I & II) water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000991/2023-2024 | 3845/ED | 04/10/2023 | 01/06/2025 | M/S, GHOSH ENTERPRISE | 23.17 | 0 | 0 | 80
26 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Additional Laying of Distribution Pipe Lines for leftout area of UDAYNARAYANPUR ZONE-II Piped Water Supply Scheme, Rising Main & Inter Connection with PH-1 & PH-5 of UDAYNARAYANPUR ZONE-I & II PWSS, Rising Main & Inter Connection with both PH-3 & PH-4 and Repairing of Pump House & Construction of W/C at H/W Site of UDAYNARAYANPUR ZONE-I & II PWSS at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. [SM/18398] | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000115/2024-2025 | 3872/HD | 04/09/2024 | 28/11/2025 | GHOSH CONCERN | 197.8 | 0 | 0 | 40
27 | HOWRAH |  | Howrah Division | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | SM/18398 | Augmentation | Work order for temporary staging, welding arrangements and some allied works for conducting NDT for Udaynarayanpur OHR of Udaynarayanpur Zone-I & II PWSS at Udaynarayanpur block under Howrah Division, PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000924/2024-2025 | 529/RWS | 10/12/2024 | 25/12/2024 | BINOY KOLEY | 0.85 | 0 | 0 | 95
Total | [13 empty] | 1855.58 | 778.82 | 41.97