## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta-I | Howrah Division | Sherpur Piped Water Supply Scheme | SM/18426 | New | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 964/HD | 28/02/2024 | 28/02/2024 | Resource Division | 65.52 | 0 | 0 | 0
2 | HOWRAH | Amta-I | Howrah Division | Sherpur Piped Water Supply Scheme | SM/18426 | New | Material Requisition To Resource Division |  |  | RTOR000034/2024-2025 | 4864/HD | 22/11/2024 | 22/11/2024 | Resource Division | 12.32 | 0 | 0 | 0
3 | HOWRAH | Amta-I | Electrical | Sherpur Piped Water Supply Scheme | SM/18426 | New | Quotation for New Service Connection at Sherpur W/S. Sch. PH-II, Amta-I |  |  | BILL/04663/2023-2024 | 640 | 09/01/2024 | 09/01/2024 | WBSEDCL | 4.17 | 0 | 0 | 0
4 | HOWRAH | Amta-I | Electrical | Sherpur Piped Water Supply Scheme | SM/18426 | New | Quotation for New Service Connection at Sherpur W/S. Sch. PH-I, Amta-I |  |  | BILL/04662/2023-2024 | 643 | 09/01/2024 | 09/01/2024 | WBSEDCL | 3.9 | 0 | 0 | 0
5 | HOWRAH | Amta-I | Electrical | Sherpur Piped Water Supply Scheme | SM/18426 | New | Quotation for New Service Connection at Sherpur W/S. Sch. PH-III, Amta-I |  |  | BILL/04664/2023-2024 | 641 | 09/01/2024 | 09/01/2024 | WBSEDCL | 6.98 | 0 | 0 | 0
6 | HOWRAH | Amta-I | Electrical | Sherpur Piped Water Supply Scheme | SM/18426 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sherpur water supply scheme, T.W. No. I, II & III, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001888/2023-2024 | 63/ED | 08/01/2024 | 28/12/2025 | MAA KALI ENTERPRISE | 34.21 | 25.37 | 74.16 | 60
7 | HOWRAH | Amta-I | Howrah Division | Sherpur Piped Water Supply Scheme | SM/18426 | New | Construction of switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement of Sherpur PWSS (4th Tube well) of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000032/2025-2026 | 2102/HD | 29/04/2025 | 13/06/2025 | MANAS MALICK | 5.95 | 0 | 0 | 0
8 | HOWRAH | Amta-I | Howrah Division | Sherpur Piped Water Supply Scheme | SM/18426 | New | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) all complete at Sherpur PWSS at Amta-I Block under Uluberia Sub Division within Howrah Division, P.H.E.Dte.(Location-Kumarchak) | AE/Ulu | JE/USD | ORD/000398/2024-2025 | 869/HD | 10/02/2025 | 22/03/2025 | AQUATECH ENGINEER | 14.16 | 0 | 0 | 100
9 | HOWRAH | Amta-I | Howrah Division | Sherpur Piped Water Supply Scheme | SM/18426 | New | Road restoration work with Bullah piling at Sherpur PWSS under Uluberia Sub Division under Howrah Division PHED. | AE/Ulu | JE/USD | ORD/000059/2025-2026 | 2494/HD | 26/05/2025 | 23/09/2025 | S.M. CONSTRUCTION | 16.06 | 0 | 0 | 100
10 | HOWRAH | Amta-I | Howrah Division | Sherpur Piped Water Supply Scheme | SM/18426 | New | Material Requisition To Resource Division |  |  | RTOR000043/2024-2025 | 157/HD | 10/01/2025 | 10/01/2025 | Resource Division | 37.03 | 0 | 0 | 0
11 | HOWRAH | Amta-I | Electrical | Sherpur Piped Water Supply Scheme | SM/18426 | New | Quotation money deposition for new service connection at Sherpur w/s scheme, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1008517850 Reference ID- 107030108 SM Code- 18426 |  |  | BILL/00291/2025-2026 |  | 16/04/2025 | 16/04/2025 | WBSEDCL | 17.69 | 0 | 0 | 0
12 | HOWRAH | Amta-I | Howrah Division | Sherpur Piped Water Supply Scheme | SM/18426 | New | Sinking of 05 (Five) nos Big dia Tube wells, Construction of Switch rooms(5.4x3.6) for HW site and other TW sites, Boundary walls, Land Developments, Laying distribution system (UPVC & HDPE & DI) & Providing Functional Household Tap Connection (FHTC), Interconnection between tubewells and OHR and Construction of OHR of 700 cum and 400 cum capacity 20.0 m staging height along with pipe connection etc for SHERPUR PWSS in Amta-I Block and Augmentation of JOARGARH PWSS in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC=8807] | AE/Ulu | JE-USD,JE/USD | ORD/000239/2023-2024 | 3488/HD | 29/09/2023 | 17/03/2026 | S.P. CONSTRUCTION | 1926.07 | 352.73 | 18.31 | 65
Total | [13 empty] | 2144.06 | 378.1 | 17.63