## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta-I | Howrah Division | Sherpur Piped Water Supply Scheme | SM/18426 | New | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 964/HD | 28/02/2024 | 28/02/2024 | Resource Division | 65.52 | 0 | 0 | 0
2 | HOWRAH | Amta-I | Howrah Division | Sherpur Piped Water Supply Scheme | SM/18426 | New | Material Requisition To Resource Division |  |  | RTOR000034/2024-2025 | 4864/HD | 22/11/2024 | 22/11/2024 | Resource Division | 12.32 | 0 | 0 | 0
3 | HOWRAH | Amta-I | Electrical | Sherpur Piped Water Supply Scheme | SM/18426 | New | Quotation for New Service Connection at Sherpur W/S. Sch. PH-II, Amta-I |  |  | BILL/04663/2023-2024 | 640 | 09/01/2024 | 09/01/2024 | WBSEDCL | 4.17 | 0 | 0 | 0
4 | HOWRAH | Amta-I | Electrical | Sherpur Piped Water Supply Scheme | SM/18426 | New | Quotation for New Service Connection at Sherpur W/S. Sch. PH-I, Amta-I |  |  | BILL/04662/2023-2024 | 643 | 09/01/2024 | 09/01/2024 | WBSEDCL | 3.9 | 0 | 0 | 0
5 | HOWRAH | Amta-I | Electrical | Sherpur Piped Water Supply Scheme | SM/18426 | New | Quotation for New Service Connection at Sherpur W/S. Sch. PH-III, Amta-I |  |  | BILL/04664/2023-2024 | 641 | 09/01/2024 | 09/01/2024 | WBSEDCL | 6.98 | 0 | 0 | 0
6 | HOWRAH | Amta-I | Electrical | Sherpur Piped Water Supply Scheme | SM/18426 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sherpur water supply scheme, T.W. No. I, II & III, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001888/2023-2024 | 63/ED | 08/01/2024 | 28/12/2025 | MAA KALI ENTERPRISE | 34.21 | 25.37 | 74.16 | 60
7 | HOWRAH | Amta-I | Howrah Division | Sherpur Piped Water Supply Scheme | SM/18426 | New | Construction of switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement of Sherpur PWSS (4th Tube well) of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000032/2025-2026 | 2102/HD | 29/04/2025 | 13/06/2025 | MANAS MALICK | 5.95 | 0 | 0 | 0
Total | [13 empty] | 133.06 | 25.37 | 19.07