## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Udaynarayanpur | Howrah Division | Bedhi Chandrapur Piped Water Supply Scheme | SM/18490 | New | Preparation of DPR for new piped water supply scheme of Bedhichandrapur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu |  | ORD/000254/2022-2023 | 328/AE/USD | 16/08/2022 | 30/09/2022 | APEX ENGINEERING | 2.81 | 2.8 | 99.52 | 100
2 | HOWRAH | Udaynarayanpur | Howrah Division | Bedhi Chandrapur Piped Water Supply Scheme | SM/18490 | New | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 3217/HD | 05/09/2023 | 05/09/2023 | Resource Division | 16.59 | 0 | 0 | 0
3 | HOWRAH | Udaynarayanpur | Electrical | Bedhi Chandrapur Piped Water Supply Scheme | SM/18490 | New | Quotation bill for new service connection charge for Bedhi Chandrapur PWSS TW - I |  |  | BILL/04434/2023-2024 | 498 | 07/12/2023 | 07/12/2023 | WBSEDCL | 3.4 | 0 | 0 | 0
4 | HOWRAH | Udaynarayanpur | Electrical | Bedhi Chandrapur Piped Water Supply Scheme | SM/18490 | New | Quotation bill for new service connection charge for Bedhi Chandrapur PWSS TW - II |  |  | BILL/04435/2023-2024 | 497 | 07/12/2023 | 07/12/2023 | WBSEDCL | 10.33 | 0 | 0 | 0
5 | HOWRAH | Udaynarayanpur | Howrah Division | Bedhi Chandrapur Piped Water Supply Scheme | SM/18490 | New | Sinking of 2nos 250 X 150mm dia Tube Well 230 mtr,Construction of 2nos Pump House cum switch room with sanitary arrangement, Laying Distribution system (LDS) with necessary inter-connections with OHR and bypass arrangement etc. all complete, Functional Household Tap Connection (FHTC) works, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Drawing No- PC-I/O.H.R/7/2012)with necessary soil investigation with foundation design as per soil test report for BEDHI CHANDRAPUR PWSS at Udaynarayanpur Block under Uluberia Sub-Division under, Howrah Division, P. H. E. Dte. | AE/RWS | JE/RWS/Amta II,JE/RWS/Udaynaryanpur,JE Sadar | ORD/000137/2023-2024 | 2758/HD | 31/07/2023 | 01/08/2026 | JAHANGIR ALAM | 335.32 | 152.52 | 45.48 | 42
6 | HOWRAH | Udaynarayanpur | Howrah Division | Bedhi Chandrapur Piped Water Supply Scheme | SM/18490 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 19/03/2025 | HORIZEN | 13.59 | 0 | 0 | 60
7 | HOWRAH | Udaynarayanpur | Howrah Division | Bedhi Chandrapur Piped Water Supply Scheme | SM/18490 | New | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site along with restoration work of damaged pipeline of BEDHICHANDRAPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | AE/RWS |  | ORD/000018/2025-2026 | 1939/HD | 22/04/2025 | 06/06/2025 | JAHANGIR ALAM | 47.81 | 0 | 0 | 0
8 | HOWRAH | Udaynarayanpur | Howrah Division | Bedhi Chandrapur Piped Water Supply Scheme | SM/18490 | New | Rising Main & Inter Connection with both tube wells of BEDHICHANDRAPUR PWSS in Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS | JE/RWS/Amta II | ORD/000129/2025-2026 | 3224/HD | 22/07/2025 | 06/08/2025 | MJ ENTERPRISE | 9.94 | 0 | 0 | 100
9 | HOWRAH | Udaynarayanpur | Electrical | Bedhi Chandrapur Piped Water Supply Scheme | SM/18490 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bedhi Chandrapur water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000822/2023-2024 | 3177/ED | 28/07/2023 | 01/10/2024 | NEW RANBEE ENGINEERING | 21.38 | 20.91 | 97.81 | 85
Total | [13 empty] | 461.17 | 176.22 | 38.21