## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 36.76 | 0 | 0 | 0
2 | HOWRAH |  | Electrical | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II Block: Panchla, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000921/2023-2024 | 3592/ED | 28/08/2023 | 26/11/2023 | R.N.S. TRADING | 43.65 | 0 | 0 | 0
3 | HOWRAH |  | Electrical | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. III and Zone-II, T.W. No. III Block: Panchla, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000875/2023-2024 | 3448/ED | 11/08/2023 | 09/11/2023 | R.M.D TRADING. | 21.99 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 446/HD | 06/02/2023 | 06/02/2023 | Resource Division | 86.28 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection-1818 NOS) For Augmentation of Deulpur Gangadharpur Zone-I PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 7-34 to Node Section 74-77, From Node Section 101-248 to Node Section 356-358, From Node Section 72-84 to Node Section 241-256, From Node Section 256-257 to Node Section 449-450 (P-5,6,7 & 8) | AE/SADAR | je_how_rws_jagat | ORD/000151/2023-2024 | 2956/HD | 16/08/2023 | 31/07/2026 | M/S ASHIRBAD (INDIA) | 179.05 | 0 | 0 | 85
6 | HOWRAH |  | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Deulpur Gangadharpur (Zone-I) PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000340/2023-2024 | 4597/HD | 20/12/2023 | 03/02/2024 | WATER TECH | 50.26 | 0 | 0 | 100
7 | HOWRAH |  | Electrical | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Quotation App. No.-1007748306 SM/18560 |  |  | BILL/00467/2024-2025 | 118 | 17/05/2024 | 17/05/2024 | WBSEDCL | 6.52 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Construction of 700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/8/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection)For Deulpur Gangadharpur Zone-I PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte.,Part 1 From Node Section R1-1 to Node Section 21-22 to Section 202-204 | AE/SADAR | je_how_rws_jagat | ORD/000144/2023-2024 | 2838/HD | 07/08/2023 | 29/03/2025 | SUJATA CONSTRUCTION | 373.91 | 0 | 0 | 24
9 | HOWRAH |  | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) For Augmentation of Deulpur Gangadharpur Zone-I PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 174-242 to Node Section 411-414, Part 4 | AE/SADAR | je_how_rws_jagat | ORD/000215/2023-2024 | 3279/HD | 13/09/2023 | 11/01/2024 | MAA TARA CONSTRUCTION | 98.18 | 0 | 0 | 70
10 | HOWRAH |  | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 14/12/2025 | TECH VISION | 12.48 | 0 | 0 | 62
11 | HOWRAH |  | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Special repairing work for restoration of damage pavement caused by laying of pipe line from start Node point 36 to End Node point 256 of existing LDS at Deulpur Board Girls primary School to Deulpur Bandher Bazar for the 2.0 km (PMGSY/PWD) road at Deulpur Gangadharpur Zone-I PWSS Under Panchla Block under Howrah Sadar Sub Division of Howrah Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000710/2024-2025 | 1313/HD | 10/03/2025 | 08/07/2025 | ASSOCIATE CONSTRUCTION | 28.9 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Laying of additional distribution pipe line & allied works at Deulpur Gangadharpur Zone-I PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR | je_how_rws_jagat | ORD/000399/2024-2025 | 859/HD | 07/02/2025 | 03/05/2026 | M/S ASHIRBAD (INDIA) | 87.3 | 0 | 0 | 40
13 | HOWRAH |  | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Laying Distribution Pipeline work with Providing FHTC (1300 nos) (Functional Household Tap Connection) For Augmentation of Deulpur Gangadharpur Zone-I PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P.H.E. Dte. From Node Section 55-82 to Node Section 147-148 & From Node Section 82-170 to Node Section 409-410 (P-2&3) | AE/SADAR | je_how_rws_jagat | ORD/000193/2023-2024 | 3195/HD | 04/09/2023 | 01/02/2025 | SANJUKTA ENGINEERS | 121.57 | 0 | 0 | 55
14 | HOWRAH |  | Howrah Division | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18560 | Augmentation | Laying of additional distribution pipe line and allied works in Kusadanga mouza at Deulpur Gangadharpur Zone-I PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. | AE/SADAR | je_how_rws_jagat | ORD/000161/2024-2025 | 4187/HD | 26/09/2024 | 24/05/2025 | MAA TARA CONSTRUCTION | 53.88 | 0 | 0 | 80
Total | [13 empty] | 1200.75 | 0 | 0