## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Preparation of DPR for new piped W/S scheme of Ajangachi PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000221/2022-2023 | 315/AE/USD | 16/08/2022 | 30/09/2022 | VOYAGER | 3.85 | 3.85 | 100 | 0
2 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nawapara PWSS (2nos) & Ajangachi PWSS (2nos) & Jhikira PWSS (2nos) of Amta-II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/BLK/amta2,JE/USD | ORD/000238/2023-2024 | 3440/HD | 26/09/2023 | 25/11/2023 | PRANTIK DRILLING AGENCY | 77.89 | 25.28 | 32.46 | 100
3 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 1286/HD | 13/03/2024 | 13/03/2024 | Resource Division | 58.29 | 0 | 0 | 0
4 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Material Requisition To Resource Division |  |  | RTOR000032/2024-2025 | 4864/HD | 22/11/2024 | 22/11/2024 | Resource Division | 5.54 | 0 | 0 | 0
5 | HOWRAH | Amta-II | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Quotation for new service connection at TW no. 2 of Ajangachi w/s scheme, Amta-II, Howrah Application No. 1007513650 Ref id:106459509 SM/18561 |  |  | BILL/06074/2023-2024 | 749 | 16/02/2024 | 16/02/2024 | WBSEDCL | 4.16 | 0 | 0 | 0
6 | HOWRAH | Amta-II | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Quotation Bill for New Service Connection at Ajangachi W/S. Sch.PH-I |  |  | BILL/05722/2023-2024 | 707 | 25/01/2024 | 25/01/2024 | WBSEDCL | 10.69 | 0 | 0 | 0
7 | HOWRAH | Amta-II | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Additional Quotation money for new service connection of Ajangachi w/s scheme, PH No. 2, Block- Amta-II, Howrah Application ID: 100000103588 Reference ID: 860295388 SM/18561 |  |  | BILL/00033/2024-2025 | 25 | 05/04/2024 | 05/04/2024 | WBSEDCL | 3.39 | 0 | 0 | 0
8 | HOWRAH | Amta-II | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Quotation for new service connection at TW no. 2 of Ajangachi w/s scheme, Amta-II, Howrah |  |  | BILL/06076/2023-2024 | 750 | 16/02/2024 | 16/02/2024 | WBSEDCL | 4.33 | 0 | 0 | 0
9 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Laying Distribution System & Providing House Hold Tap Connection (FHTC) & 450 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including foundation design of AJANGACHI PWSS in AMTA-II Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000180/2023-2024 | 2949/HD | 16/08/2023 | 15/08/2025 | GEE BEE NIRMAN CO PVT LTD | 817.6 | 299.94 | 36.69 | 60
10 | HOWRAH | Amta-II | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ajangachhi water supply scheme, T.W. No.- I, II & III, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000924/2023-2024 | 3595/ED | 28/08/2023 | 31/03/2025 | P.K. ENGINEERING | 32.24 | 0 | 0 | 60
11 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Construction of approach Road including restoration of CC road with Bullah piling and shifting of DI(K-7/K-9) pipes near TantiparaHazrapara of Ajangachi PWSS of Amta-II Block under Uluberia Sub Division under Howrah Divison PHE Dte. | AE/Ulu | JE/USD | ORD/000912/2024-2025 | 1763/AE/USD | 05/03/2025 | 04/04/2025 | S R TRADING CORPORATION | 4.61 | 0 | 0 | 0
12 | HOWRAH | Amta-II | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for AJANGACHI water supply scheme, TW No. IV, Block: Amta-II, District - Howrah under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/003105/2024-2025 | 488/ED | 18/03/2025 | 16/06/2025 | MAA KALI ENTERPRISE | 11.29 | 0 | 0 | 0
13 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Additional laying distribution pipeline with DI(K-7) and HDPE(PE-100,PN6) at Ajangachi PWSS of Amta-II Block in Uluberia Sub Division, under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000280/2025-2026 | 4414/HD | 25/11/2025 | 24/01/2026 | GEE BEE NIRMAN COMPANY PVT. LTD. | 65.24 | 0 | 0 | 0
14 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 250m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ajangachhi PWSS (SM/18561) of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E.Dte. | AE/Ulu | JE/USD | ORD/000135/2024-2025 | 4061/HD | 18/09/2024 | 17/11/2024 | LOKENATH ENTERPRISES | 12.81 | 0 | 0 | 100
15 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Sinking of 1(One) No. additional T.Well size (250 X 150mm) Dia and 230m deep, Drilling by Direct Rotary method with UPVC Pipes all complete at Ajangachi PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Location: Solbaga) | AE/Ulu | JE/USD | ORD/000358/2024-2025 | 270/HD | 15/01/2025 | 15/04/2025 | PRANTIK DRILLING AGENCY | 14.6 | 0 | 0 | 100
16 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Construction of 2 storied switch room SLOPE ROOF ( 5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site of Ajangachi PWSS of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000339/2024-2025 | 5019/HD | 04/12/2024 | 02/02/2025 | M/S M.R ENTERPRISE | 11.25 | 0 | 0 | 100
17 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Construction of boundary wall at 3rd Tube Well site Ajangachi PWSS (SM/18561) scheme under Amta-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000340/2024-2025 | 5059/HD | 09/12/2024 | 09/03/2025 | SUNIL ENTERPRISE | 7.62 | 0 | 0 | 100
18 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Construction of boundary wall at 2nd Tube Well site Ajangachi PWSS (SM/18561) scheme under Amta-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000343/2024-2025 | 5208/HD | 12/12/2024 | 26/01/2025 | M/S MJA ENTERPRISE | 7.62 | 7.59 | 99.69 | 100
19 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Construction of boundary wall at HW Site Ajangachi PWSS (SM/18561) scheme under Amta-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000344/2024-2025 | 5209/HD | 12/12/2024 | 10/02/2025 | A.N ROY & CO | 14.8 | 0 | 0 | 100
20 | HOWRAH | Amta-II | Howrah Division | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Construction of switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement at Head Work site of Ajangachi PWSS (2nd Tube well) of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000249/2024-2025 | 4733/HD | 12/11/2024 | 27/12/2024 | NOBLE ENTERPRISE | 5.81 | 5.57 | 95.79 | 100
21 | HOWRAH | Amta-II | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | NPC IRO-Assistant Engg HMSD PHE Ajangachi w/s scheme at Ajangachi Application No- 100000127092 Reference ID- 860322152 SM Code- 18561 |  |  | BILL/02903/2024-2025 | 672 | 21/01/2025 | 21/01/2025 | WBSEDCL | 0.33 | 0 | 0 | 0
22 | HOWRAH | Amta-II | Electrical | Ground Water Based Water Supply Scheme for Ajangachhi PWSS | SM/18561 | New | Quotation money deposition for new service connection at Ajangachi w/s scheme, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1008418424 Reference ID- 106964930 SM Code- 18561 |  |  | BILL/03361/2024-2025 | 743 | 27/03/2025 | 27/03/2025 | WBSEDCL | 5.2 | 0 | 0 | 0
Total | [13 empty] | 1179.13 | 342.23 | 29.02