## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta-I | Electrical | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Quotation Bill for New Service Connection at Debandi W/S. Sch. PH-II |  |  | BILL/04440/2023-2024 | 513 | 08/12/2023 | 08/12/2023 | WBSEDCL | 4.08 | 0 | 0 | 0
2 | HOWRAH | Amta-I | Electrical | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Quotation Bill for New Service Connection at Debandi W/S. Sch. PH-I |  |  | BILL/04439/2023-2024 | 514 | 08/12/2023 | 08/12/2023 | WBSEDCL | 3.75 | 0 | 0 | 0
3 | HOWRAH | Amta-I | Electrical | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Quotation Bill for New Service Connection at Debandi W/S. Sch. PH-III |  |  | BILL/04441/2023-2024 | 512 | 08/12/2023 | 08/12/2023 | WBSEDCL | 4.27 | 0 | 0 | 0
4 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC-1030 nos) FOR DEBANDI PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. Part-C-Debandi | AE/Ulu | JE/BLK/amta1 | ORD/000175/2023-2024 | 2948/HD | 14/08/2023 | 08/08/2024 | JOY CHANDI CONSTRUCTION | 166.89 | 0 | 0 | 50
5 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Laying Distribution System(HDPE & DI) & Providing Functional Household Tap Connection (FHTC-1450 nos) FOR DEBANDI PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. Part-D-Uttar Ramchandrapur & Anule | AE/Ulu | JE/BLK/amta1 | ORD/000192/2023-2024 | 3194/HD | 04/09/2023 | 01/04/2025 | A P POWER & CONCRETE | 182.91 | 0 | 0 | 30
6 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Work Order for Preparation of DPR for new piped water supply scheme of Debandi PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/BLK/amta1 | ORD/000439/2021-2022 | 240/HD | 07/02/2022 | 22/02/2022 | RADIANT | 4.4 | 0 | 0 | 100
7 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Debandi PWSS of Amta-I Block Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/BLK/amta1 | ORD/000189/2023-2024 | 3126/HD | 29/08/2023 | 13/10/2023 | SPG ENTERPRISES | 52.15 | 0 | 0 | 100
8 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Construction of Kiosk (one no) at Debandi PWSS under uluberia Sub-Division, under Howrah DivisionP.H.E.Dte.(Size in side 3.0x1.8m)at 2nd TW Site at Baneswarpur Mouza. | AE/Ulu | JE/BLK/amta1 | ORD/000671/2023-2024 | 3234/AE/USD | 12/03/2024 | 11/04/2024 | NOBLE ENTERPRISE | 1.13 | 0 | 0 | 100
9 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Construction of Kiosk (one no) at Debandi PWSS under uluberia Sub-Division, under Howrah Division P.H.E.Dte.(Size in side 3.0x1.8m) at 3rd TW Site at Debandi Mouza | AE/Ulu | JE/BLK/amta1 | ORD/000690/2023-2024 | 3232/AE/USD | 12/03/2024 | 11/04/2024 | PRADIP KUMAR HAJRA | 1.13 | 0 | 0 | 100
10 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Construction of Kiosk (one no) at Debandi PWSS underuluberia Sub-Division, under Howrah Division P.H.E Dte.(Size in side 3.0x1.8m) at HW Site at Sarpota Mouza | AE/Ulu | JE/BLK/amta1 | ORD/000691/2023-2024 | 3233/AE/USD | 12/03/2024 | 11/04/2024 | MAA TARA ENTERPRISE | 1.13 | 0 | 0 | 100
11 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 170/HD | 15/01/2024 | 15/01/2024 | Resource Division | 12.87 | 0 | 0 | 0
12 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 447/HD | 01/02/2024 | 01/02/2024 | Resource Division | 52.51 | 0 | 0 | 0
13 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Road Restoration work due to road cutting by PHED for laying water pipe line at Howrah Amta Road from 37.40 Km to 41.30 Km under Howrah Division, PWD during the year 2024-2025 |  |  | BILL/00804/2024-2025 | BP-2024-25-479 | 06/11/2024 | 06/11/2024 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 11.45 | 0 | 0 | 0
14 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC-470 nos) FOR DEBANDI PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. Part-E-Kandua | AE/Ulu | JE/BLK/amta1 | ORD/000247/2023-2024 | 3531/HD | 04/10/2023 | 23/09/2025 | M/S. BHOWMICK ENTERPRISE | 68.87 | 0 | 0 | 0
15 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Construction of Boundary Wall (284 m Length), Land development, approach road etc at Head Work Site including alternative laying of DI(K-9) & DI (K-7) pipeline etc of 2nd T.Well & 3rd T.Well site of Debandi W/S scheme at Amta-I Block in Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000131/2025-2026 | 3233/HD | 23/07/2025 | 21/09/2025 | MAA TARA CONSTRUCTION | 53.51 | 0 | 0 | 0
16 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Sinking of 1 (one) No. Additional 250 X 150 mm Dia and 250 m deep Drilling by Direct Rotary method with UPVC Pipes all complete at Debandi PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Location: Darapur) | AE/Ulu |  | ORD/000130/2025-2026 | 3232/HD | 23/07/2025 | 22/08/2025 | AUXILIARY TUBEWELL DRILLERS | 15.45 | 0 | 0 | 0
17 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Amta-I Block) (PART-B) | AE HQ |  | ORD/000228/2025-2026 | 4126/HD | 14/10/2025 | 13/11/2025 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
18 | HOWRAH | Amta-I | Electrical | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Debandi water supply scheme, T.W. No.- I, II & III, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5,Junior Engineer6 | ORD/000909/2023-2024 | 3580/ED | 28/08/2023 | 30/06/2025 | S.S. ENTERPRISES | 34.16 | 0 | 0 | 60
19 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC 690 nos) DEBANDI PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. Part-B-Sarpota & Chalunia | AE/Ulu | JE/BLK/amta1 | ORD/000165/2023-2024 | 2999/HD | 18/08/2023 | 08/07/2025 | M/S SARADA UDYOG | 138.83 | 0 | 0 | 60
20 | HOWRAH | Amta-I | Howrah Division | DEBANDI PIPED WATER SUPPLY SCHEMES, AMTA-I BLOCK, HOWRAH | SM/18562 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 17/02/2025 | TECH VISION | 12.67 | 0 | 0 | 100
Total | [13 empty] | 826.96 | 0 | 0