## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Panchla | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. | SM/18563 | New | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 38.2 | 0 | 0 | 0
2 | HOWRAH | Panchla | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. | SM/18563 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Panchla PWSS (Mouza-Panchla (CT) of Panchla Block under Howrah Division PHE Dte. | AE/SADAR |  | ORD/000077/2022-2023 | 1020/HD | 05/05/2022 | 20/05/2022 | ENVIROTECH SOLUTIONS | 2.53 | 0 | 0 | 100
3 | HOWRAH | Panchla | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. | SM/18563 | New | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 446/HD | 06/02/2023 | 06/02/2023 | Resource Division | 62.61 | 0 | 0 | 0
4 | HOWRAH | Panchla | Electrical | PANCHLA PIPED WATER SUPPLY SCHEME. | SM/18563 | New | Quotation money deposition for new service connection at Panchla w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1007951166 Reference ID- 106680336 SM Code- 18563 |  |  | BILL/01982/2024-2025 | 489 | 01/10/2024 | 01/10/2024 | WBSEDCL | 3.43 | 0 | 0 | 0
5 | HOWRAH | Panchla | Electrical | PANCHLA PIPED WATER SUPPLY SCHEME. | SM/18563 | New | Quotation money deposition for new service connection at Panchla pwss, Dist-Howrah, under PHED. App. No.-1007554361 Ref. No.-106486310 SM/18563 |  |  | BILL/06212/2023-2024 | 817 | 01/03/2024 | 01/03/2024 | WBSEDCL | 5.05 | 0 | 0 | 0
6 | HOWRAH | Panchla | Electrical | PANCHLA PIPED WATER SUPPLY SCHEME. | SM/18563 | New | Quotation money deposition for shifting of 1 mtr. pcc pole and others allied works at panchla pwss. near P.H No.-I under ED PHED. Ref. NO.-860314452 SM/18563 |  |  | BILL/02032/2024-2025 | BP-24-25-591 | 20/11/2024 | 20/11/2024 | WBSEDCL | 0.45 | 0 | 0 | 0
7 | HOWRAH | Panchla | Electrical | PANCHLA PIPED WATER SUPPLY SCHEME. | SM/18563 | New | Quotation money deposition for new service connection at PANCHLA pwss, T.W No.-I , Dist-Howrah under ED PHED. App. No.-1007505290 Ref. ID.: 106463795 SM/18563 |  |  | BILL/06204/2023-2024 | 815 | 28/02/2024 | 28/02/2024 | WBSEDCL | 4.43 | 0 | 0 | 0
8 | HOWRAH | Panchla | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. | SM/18563 | New | Different Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, and Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Panchla Block, District:-Howrah [NEW SCHEME][Name of Schemes:-1)Paschim Panchla PWSS 2) Panchla PWSS 3) Gabberia-Mallik Bagan PWSS]. | AE/SADAR | je_how_rws_jagat,JE Sadar | ORD/000148/2023-2024 | 2866/HD | 08/08/2023 | 03/02/2026 | SAMIRON GHOSH | 1986.19 | 0 | 0 | 30
9 | HOWRAH | Panchla | Electrical | PANCHLA PIPED WATER SUPPLY SCHEME. | SM/18563 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Panchla water supply scheme, T.W. No.- I, II, III & IV, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000910/2023-2024 | 3581/ED | 28/08/2023 | 02/08/2025 | WEST BENGAL ENGINEERING CO. | 46.35 | 0 | 0 | 30
10 | HOWRAH | Panchla | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. | SM/18563 | New | Additional Laying Distribution Pipeline & approach road with land development at OHR site & allied works of Panchla PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat,JE Sadar | ORD/000030/2024-2025 | 2835/HD | 20/06/2024 | 10/02/2026 | SAMIRON GHOSH | 66.05 | 0 | 0 | 20
11 | HOWRAH | Panchla | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. | SM/18563 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 14/12/2025 | TECH VISION | 12.48 | 0 | 0 | 62
12 | HOWRAH | Panchla | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. | SM/18563 | New | Special repairing work for restoration of damage pavement caused by laying of pipe line from Start Node Section 359 to End Node section 873 of existing LDS at MEJUTI BRIDGE TO PANCHLA BAZAR for the 2.7 km (WBSRDA) road at Panchla PWSS in Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR |  | ORD/000112/2025-2026 | 3144/HD | 15/07/2025 | 13/09/2025 | LAKSHMI IRON | 37.39 | 0 | 0 | 0
13 | HOWRAH | Panchla | Howrah Division | PANCHLA PIPED WATER SUPPLY SCHEME. | SM/18563 | New | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bally Jagacha & Panchla Block) | AE HQ |  | ORD/000220/2025-2026 | 4118/HD | 14/10/2025 | 13/11/2025 | JHARNA ENTERPRISE | 4.79 | 0 | 0 | 0
Total | [13 empty] | 2269.96 | 0 | 0