## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Uluberia-II | Electrical | Baniban Zone-III Piped water Supply Scheme | SM/18564 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniban water supply scheme, Zone-III, T.W. No. I, II, III & IV, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000927/2023-2024 | 3598/ED | 28/08/2023 | 26/11/2023 | DEY ENTERPRISE | 42.99 | 0 | 0 | 0
2 | HOWRAH | Uluberia-II | Howrah Division | Baniban Zone-III Piped water Supply Scheme | SM/18564 | New | Preparation of DPR for new piped water supply scheme of Basudebpur PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte.( Banibon, Zone-III) | AE/Ulu | JE-USD | ORD/000251/2022-2023 | 325/AE/USD | 16/08/2022 | 30/09/2022 | APEX ENGINEERING | 3.76 | 3.76 | 100 | 100
3 | HOWRAH | Uluberia-II | Howrah Division | Baniban Zone-III Piped water Supply Scheme | SM/18564 | New | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Uluberia - II block of Uluberia Sub Division under Howrah Division, P.H.E. Dte. | AE HQ | je_blk_ballyjag_how | ORD/000653/2023-2024 | 1212/HD | 11/03/2024 | 26/03/2024 | TRIMARV SOLUTIONS PRIVATE LIMITED | 1.85 | 1.63 | 88.06 | 100
4 | HOWRAH | Uluberia-II | Howrah Division | Baniban Zone-III Piped water Supply Scheme | SM/18564 | New | Sinking of 3 (Three) Nos. 250 X 150 mm Dia tubewell Drilling by Direct Rotary method with UPVC Pipes all complete, Construction of 3no 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement, Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around head work site, Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site land development of Head work site and other Tube well sites, Laying distribution system (HDPE & DI) & Providing Household Connection (3191nos), Interconnection between Tube wells & OHR and Construction of 700 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation Baniban with foundation design Baniban Piped Water Supply Scheme (Zone-III) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE-USD | ORD/000152/2023-2024 | 2960/HD | 16/08/2023 | 07/06/2026 | SAMIRON GHOSH | 1022.24 | 0 | 0 | 55
5 | HOWRAH | Uluberia-II | Howrah Division | Baniban Zone-III Piped water Supply Scheme | SM/18564 | New | Restoration of Bituminous Road along with alterntive laying of DI & HDPE (PE 100, PN6) pipes from 1) Basudebpur Lalpool to Basudebpur G.P. Office via. H/W site to Jhuri Battala(PWD), 2) Basudebpur Battala to Basudebpur Shibtala, 3) Nurullapara Battala to Katra Bazar via. Katra Auto Stand, 4) Katra Auto stand to Basudebpur Lalpool, 5) Basudebpur Bazar to Tehatta Mollickpara via. Tehatta Sishu Niketan to Tehatta Balika Vidyalaya, 6) Uttar Magurkhali to Dakshin Magurkhali, 7) Adharmanik IOCL crossing to Adharmanik Pry. School via. Adharmanik HKKS Pry. School & Pramanick para under Baniban Zone-III PWSS under Uluberia Sub-Division of Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000147/2025-2026 | 3467/HD | 12/08/2025 | 11/10/2025 | INDICON ENGINEERS CO-OP SOCIETY LTD | 83.93 | 0 | 0 | 0
6 | HOWRAH | Uluberia-II | Howrah Division | Baniban Zone-III Piped water Supply Scheme | SM/18564 | New | Restoration of Black top Road along with alternative laying of DI & HDPE (PE100, PN6) pipes from Basudevpur Bazar to Nurillapara under Baniban (Zone-III) PWSS under Uluberia Sub-Division of Howrah Division, PHE Dte. (SM/18564) | AE/Ulu | JE-USD | ORD/000063/2025-2026 | 2501/HD | 26/05/2025 | 25/06/2025 | SANJOY GHOSH | 9.16 | 0 | 0 | 100
7 | HOWRAH | Uluberia-II | Howrah Division | Baniban Zone-III Piped water Supply Scheme | SM/18564 | New | Material Requisition To Resource Division |  |  | RTOR000047/2024-2025 | 494/HD | 24/01/2025 | 24/01/2025 | Resource Division | 11.09 | 0 | 0 | 0
8 | HOWRAH | Uluberia-II | Howrah Division | Baniban Zone-III Piped water Supply Scheme | SM/18564 | New | Material Requisition To Resource Division |  |  | RTOR000045/2024-2025 | 493/HD | 24/01/2025 | 24/01/2025 | Resource Division | 35.82 | 0 | 0 | 0
9 | HOWRAH | Uluberia-II | Electrical | Baniban Zone-III Piped water Supply Scheme | SM/18564 | New | Quotation money deposition for new service connection at Baniban w/s scheme, Zone- III, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008447246 Reference ID- 106985415 SM Code- 18564 |  |  | BILL/04301/2024-2025 |  | 20/03/2025 | 20/03/2025 | WBSEDCL | 4.2 | 0 | 0 | 0
10 | HOWRAH | Uluberia-II | Howrah Division | Baniban Zone-III Piped water Supply Scheme | SM/18564 | New | Road Restoration work due to cutting by PHE for laying water pipeline at Howrah Amta Road from 44.80 km to 47.30 km under Howrah Division, P.W.D. during the year 2025-26. |  |  | BILL/00902/2025-2026 |  | 10/10/2025 | 10/10/2025 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 19.97 | 0 | 0 | 0
11 | HOWRAH | Uluberia-II | Howrah Division | Baniban Zone-III Piped water Supply Scheme | SM/18564 | New | Road Restoration Work due to road cutting by PHE for laying water pipeline at Nimdighi Basudevpur Road from 2.37 kmp to 6.77 kmp in the District of Howrah during the year 2025-26. |  |  | BILL/00903/2025-2026 |  | 10/10/2025 | 10/10/2025 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 28.53 | 0 | 0 | 0
12 | HOWRAH | Uluberia-II | Howrah Division | Baniban Zone-III Piped water Supply Scheme | SM/18564 | New | Continuation order for Hiring of 1 (One) no. Luxury Taxi/Maxi cab/Motor cab on daily basis under monthly hiring category for the Assistant Engineer, Uluberia Sub- Division , PHE Dte of the Government of West Bengal (for Twelve months) under Howrah Division, PHE dte. (Period of 365 Days) | AE/Ulu | JE-USD,JE/USD | ORD/000390/2024-2025 | 1182/AE/USD | 27/11/2024 | 27/11/2025 | NOBLE ENTERPRISE | 4.8 | 1.77 | 36.76 | 30
Total | [13 empty] | 1268.35 | 7.16 | 0.56