## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme | SM/18565 | Augmentation | Preparation of DPR for Augmentation of Harop PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | je/blk/bagn1 | ORD/000223/2022-2023 | 316/AE/USD | 16/08/2022 | 30/09/2022 | MS SOBHA AND CO | 3.48 | 0 | 0 | 90
2 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme | SM/18565 | Augmentation | Sinking of 5 (Five) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Harop PWSS Zone -I (1 no) & Zone-II (2 nos) & Matinala PWSS (2 nos) of Bagnan-I Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE-USD,je/blk/bagn1,JE/USD | ORD/000249/2023-2024 | 3533/HD | 04/10/2023 | 03/12/2023 | AQUATECH ENGINEERS | 64.95 | 0 | 0 | 40
3 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme | SM/18565 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 170/HD | 15/01/2024 | 15/01/2024 | Resource Division | 11.4 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme | SM/18565 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2024-2025 | 4864/HD | 22/11/2024 | 22/11/2024 | Resource Division | 6.16 | 0 | 0 | 0
5 | HOWRAH |  | Electrical | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme | SM/18565 | Augmentation | Quotation for new service connection of Harop W/S. Sch. PH-I |  |  | BILL/06053/2023-2024 | 753 | 16/02/2024 | 16/02/2024 | WBSEDCL | 4.08 | 0 | 0 | 0
6 | HOWRAH |  | Electrical | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme | SM/18565 | Augmentation | Quotation for new service connection of Harop W/S. Sch. PH-II |  |  | BILL/06046/2023-2024 | 746 | 08/02/2024 | 08/02/2024 | WBSEDCL | 6.37 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme | SM/18565 | Augmentation | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells & Construction of 4 nos 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement and 400 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design of HAROP (ZONE-II) PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu | je/blk/bagn1 | ORD/000147/2023-2024 | 2846/HD | 07/08/2023 | 01/04/2026 | SUBHASH BOSE | 506.25 | 0 | 0 | 35
8 | HOWRAH |  | Electrical | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme | SM/18565 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Harop (Zone-I & II) water supply scheme, T.W. No. I, II & III, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000922/2023-2024 | 3593/ED | 28/08/2023 | 01/05/2025 | SUBHRA ENTERPRISE | 32.24 | 0 | 0 | 50
Total | [13 empty] | 634.92 | 0 | 0