## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Uluberia-II | Electrical | Baniban Zone-I Piped Water Supply Scheme | SM/18566 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniban (Zone-I) water supply scheme, T.W. No.- I, II, III & IV, Block: Uluberia-II District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000911/2023-2024 | 3582/ED | 28/08/2023 | 26/11/2023 | D. K. ELECTRIC | 42.71 | 0 | 0 | 0
2 | HOWRAH | Uluberia-II | Howrah Division | Baniban Zone-I Piped Water Supply Scheme | SM/18566 | New | Sinking of 4 (Four) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete, 4no 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement, Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around head work site, Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site, land development of Head work site and other Tube well sites, Laying distribution system (HDPE & DI) & Providing Household Connection, Interconnection between Tube wells & 700 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design For Baniban Piped Water Supply Scheme (Zone-I) in Uluberia-II Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/Ulu | JE-USD | ORD/000153/2023-2024 | 2963/HD | 16/08/2023 | 01/02/2026 | SAMIRON GHOSH | 1019.91 | 0 | 0 | 0
Total | [13 empty] | 1062.62 | 0 | 0