## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Udang water supply scheme, T.W. No. I & II, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000923/2023-2024 | 3594/ED | 28/08/2023 | 26/11/2023 | EMCON | 21.49 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Work for Preparation of DPR for Augmentation of Udong PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000219/2022-2023 | 314/AE/USD | 16/08/2022 | 30/09/2022 | MS SOBHA AND CO | 3.83 | 0 | 0 | 100
3 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2024-2025 | 4864/HD | 22/11/2024 | 22/11/2024 | Resource Division | 9.24 | 0 | 0 | 0
4 | HOWRAH |  | Electrical | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Quotation money deposition for new service connection at Udang w/s scheme, Zone- II, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008049557 Reference ID- 106726236 SM Code- 18567 |  |  | BILL/02113/2024-2025 | 557 | 05/11/2024 | 05/11/2024 | WBSEDCL | 25.4 | 0 | 0 | 0
5 | HOWRAH |  | Electrical | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Quotation money deposition for new service connection at Udang w/s scheme, Zone- I, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1007772514 Reference ID- 106595797 SM Code- 18567 |  |  | BILL/00492/2024-2025 | 165 | 28/05/2024 | 28/05/2024 | WBSEDCL | 5.3 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells, construction of 2 nos 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at TW Sites and 450 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design for UDANG (ZONE-II) PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu | JE/USD | ORD/000145/2023-2024 | 2839/HD | 07/08/2023 | 30/11/2025 | NATURAL RESOURCES CONSORTIUM | 501.82 | 0 | 0 | 45
7 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Land Development and Approach Road at HW site of Udong Zone-II PWSS of Amta-I Block under Uluberia Sub Division under Howrah Division PHED. | AE/Ulu |  | ORD/000451/2024-2025 | 987/HD | 20/02/2025 | 22/03/2025 | NATURAL RESOURCES CONSORTIUM | 12.13 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Providing Additional Pipeline and repairing/ reconnection of existing FHTCs at Vill: Ranapara & Deorah of Udong-II G.P of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000456/2024-2025 | 989/HD | 20/02/2025 | 21/04/2025 | ADITYA HAZRA | 29.76 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Construction of boundary wall at HW Site of Udong Zone-II W/S scheme within Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000448/2024-2025 | 964/HD | 19/02/2025 | 20/04/2025 | NATURAL RESOURCES CONSORTIUM | 20.46 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Construction of boundary wall at 2nd T/W Site of Udong Zone-II W/S scheme within Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000369/2024-2025 | 705/HD | 30/01/2025 | 12/09/2025 | TIYASA ENTERPRISE | 7.68 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Land Development & Approach Road at 2nd TW site of Udong Zone-II PWSS of Amta-I Block under Uluberia Sub Division under Howrah Divison PHED. | AE/Ulu | JE/USD | ORD/000411/2024-2025 | 1482/AE/USD | 15/01/2025 | 04/02/2025 | NOBLE ENTERPRISE | 1.24 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Road restoration work with Bullah piling at Udong Zone-II PWSS of Amta-I Block under Uluberia Sub Division under Howrah Division PHED. | AE/Ulu |  | ORD/000450/2024-2025 | 986/HD | 20/02/2025 | 06/04/2025 | NATURAL RESOURCES CONSORTIUM | 20.08 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Sinking of 3(Three) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Udang Zone-I & Zone-II 2 nos under Amta-I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000191/2023-2024 | 3133/HD | 29/08/2023 | 15/03/2025 | NADIA TUBEWELLS | 38.94 | 0 | 0 | 68
14 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Laying Distribution System(HDPE & DI) & Providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells UDONG (ZONE-I) PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu | JE/USD | ORD/000159/2023-2024 | 2977/HD | 17/08/2023 | 08/04/2025 | TAPU SAHA | 410.47 | 0 | 0 | 100
15 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at 4th tube well (Replaced) site of Udang Zone-I PWSS of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | AE/Ulu | JE/USD | ORD/000194/2024-2025 | 786/AE/USD | 09/09/2024 | 09/03/2025 | DEBANANDA CONSTRUCTION | 4.72 | 0 | 0 | 100
16 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 17/02/2025 | TECH VISION | 12.67 | 0 | 0 | 100
Total | [13 empty] | 1125.24 | 0 | 0