## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Uluberia-II | Electrical | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. | SM/18747 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniban (Zone-IV) water supply scheme, New Tubewell, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000937/2023-2024 | 3616/ED | 29/08/2023 | 27/11/2023 | MAA TARA ENTERPRISE. | 10.17 | 0 | 0 | 0
2 | HOWRAH | Uluberia-II | Howrah Division | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. | SM/18747 | New | Preparation of DPR for new piped water supply scheme of Brindabanpur PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte.(Baniban, Zone-IV) | AE/Ulu | JE-USD | ORD/000249/2022-2023 | 323/AE/USD | 16/08/2022 | 30/09/2022 | APEX ENGINEERING | 3.8 | 0 | 0 | 100
3 | HOWRAH | Uluberia-II | Howrah Division | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. | SM/18747 | New | Material Requisition To Resource Division |  |  | RTOR000038/2024-2025 | 4864/HD | 22/11/2024 | 22/11/2024 | Resource Division | 7.39 | 0 | 0 | 0
4 | HOWRAH | Uluberia-II | Electrical | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. | SM/18747 | New | Quotation money deposition for new service connection at Baniban w/s scheme, Zone- IV, T.W. No.-03, Dist.-Howrah under PHE Dte. Application No- 1007829643 Reference ID- 106621794 SM Code- 18747 |  |  | BILL/01178/2024-2025 | 314 | 22/07/2024 | 22/07/2024 | WBSEDCL | 8.04 | 0 | 0 | 0
5 | HOWRAH | Uluberia-II | Electrical | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. | SM/18747 | New | Quotation money deposition for new service connection at Baniban w/s scheme, Zone- IV, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1007629084 Reference ID- 106535440 SM Code- 18747 |  |  | BILL/00324/2024-2025 | 109 | 09/05/2024 | 09/05/2024 | WBSEDCL | 3.93 | 0 | 0 | 0
6 | HOWRAH | Uluberia-II | Electrical | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. | SM/18747 | New | Deposition of quotation money for new service connection at P.H No.-I of Baniban W/S scheme, Zone-IV, Dist- Howrah under ED PHED. App. No.-1007628595 SM/18747 |  |  | BILL/00453/2024-2025 | 132 | 17/05/2024 | 17/05/2024 | WBSEDCL | 4.15 | 0 | 0 | 0
7 | HOWRAH | Uluberia-II | Howrah Division | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. | SM/18747 | New | BANIBAN (Zone-II & IV) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Uluberia-II Block, District:- Howrah [NEW SCHEME] | AE/Ulu | JE-USD | ORD/000336/2023-2024 | 4553/HD | 18/12/2023 | 17/12/2024 | LUKE ENGICON | 1736.09 | 0 | 0 | 35
8 | HOWRAH | Uluberia-II | Howrah Division | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. | SM/18747 | New | Hiring of 1 (One) no. Luxury Taxi/Maxi cab/Motor cab on daily basis under monthly hiring category for the Assistant Engineer,Uluberia Sub- Division , PHE Dte of the Government of West Bengal (for Twelve months) under Howrah Division,PHEdte. (Period of 365 Days) | AE/Ulu | JE/USD | ORD/000459/2023-2024 | 791/AE/USD | 29/11/2023 | 29/11/2024 | NOBLE ENTERPRISE | 4.81 | 0 | 0 | 40
9 | HOWRAH | Uluberia-II | Howrah Division | BANIBAN (ZONE-IV) PIPED WATER SUPPLY SCHEME. | SM/18747 | New | Continuation order for Hiring of 01 (One) no. (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer, Uluberia Sub-Division, PHE Dte. (for the period from 01.01.2024 to 31.12.2024). Car No.:-WB-135078 In continuation to the order under reference and your application dated 26/12/2023, you are requested to continue the above mentioned 'work in consultation with the Assistant Engineer, Uluberia Sub-Division, PHE Dte. | AE/Ulu | JE-USD | ORD/000623/2023-2024 | 4785/HD | 29/12/2023 | 29/12/2024 | PUTUL TRAVELS | 4.79 | 0 | 0 | 25
Total | [13 empty] | 1783.16 | 0 | 0