## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Uluberia-II | Electrical | Ground Water Based Water Supply Scheme For Baniban (Zone-II) and its adjoining areas to Accommodate FHTC in Uluberia-II Block, District - Howrah. | SM/18748 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniban (Zone-II) water supply scheme, T.W. No.- I, II, III & IV, Block: Uluberia-II District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000938/2023-2024 | 3617/ED | 29/08/2023 | 27/11/2023 | DEY ENTERPRISE | 45.74 | 0 | 0 | 0
2 | HOWRAH | Uluberia-II | Howrah Division | Ground Water Based Water Supply Scheme For Baniban (Zone-II) and its adjoining areas to Accommodate FHTC in Uluberia-II Block, District - Howrah. | SM/18748 | New | Preparation of DPR for new piped water supply scheme of Kantaberia PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte.(Baniban, Zone-II) | AE/Ulu | JE-USD | ORD/000248/2022-2023 | 322/AE/USD | 16/08/2022 | 30/09/2022 | APEX ENGINEERING | 3.55 | 3.55 | 100 | 100
3 | HOWRAH | Uluberia-II | Howrah Division | Ground Water Based Water Supply Scheme For Baniban (Zone-II) and its adjoining areas to Accommodate FHTC in Uluberia-II Block, District - Howrah. | SM/18748 | New | BANIBAN (Zone-II & IV) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Uluberia-II Block, District:- Howrah [NEW SCHEME] | AE/Ulu | JE-USD | ORD/000336/2023-2024 | 4553/HD | 18/12/2023 | 17/12/2024 | LUKE ENGICON | 1736.09 | 0 | 0 | 35
Total | [13 empty] | 1785.38 | 3.55 | 0.2