## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Source Augmentation of Majhu Khetra Water Supply Scheme | SM/18841 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of MajhuKhetra Water Supply Scheme Block- Jagatballavpur District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001296/2023-2024 | 4529/ED | 23/11/2023 | 21/02/2024 | APEX ENGINEERING & PROJECT CO. | 10.74 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Source Augmentation of Majhu Khetra Water Supply Scheme | SM/18841 | Augmentation | Reconnection of FHTC& Allied Works at Maju khetra PWSS at Jagatballavpur Block under Howrah sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR | je_how_rws_jagat | ORD/000718/2023-2024 | 160/HSSD | 12/02/2024 | 12/04/2024 | KUNAL BANERJEE | 0.9 | 0.89 | 98.73 | 100
3 | HOWRAH |  | Howrah Division | Source Augmentation of Majhu Khetra Water Supply Scheme | SM/18841 | Augmentation | Construction of Boundary Wall at Head work Site of Size-(50.00 m x 40.00 m), Reconnection of FHTC & distribution pipe line and Allied Works at Majhu Khetra PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000630/2023-2024 | 1215/HD | 11/03/2024 | 05/05/2025 | ENVOTECH INFRA SOLUTION | 56.71 | 15.2 | 26.8 | 80
4 | HOWRAH |  | Howrah Division | Source Augmentation of Majhu Khetra Water Supply Scheme | SM/18841 | Augmentation | Preparation of DPR for Source Augmentation for Maju Khetra PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P. H. E. Dte. |  |  | ORD/001011/2024-2025 | 828/HSSD | 09/08/2024 | 24/08/2024 | APEX ENGINEERING | 0.78 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Source Augmentation of Majhu Khetra Water Supply Scheme | SM/18841 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Source Augmentation of Gobindapur Piped Water Supply Scheme [SM/18843],Source Augmentation of Laskarpur Piped Water Supply Scheme [SM/18842], and Source Augmentation of Majhu Khetra Water Supply Scheme [SM/18841] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/000987/2024-2025 | 233-A/HSSD | 28/02/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
6 | HOWRAH |  | Howrah Division | Source Augmentation of Majhu Khetra Water Supply Scheme | SM/18841 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Gobindapur PWSS [SM/18843], Laskarpur PWSS [SM/18842], and Majhu Khetra PWSS [SM/18841] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/000999/2024-2025 | 232/HSSD | 28/02/2025 | 15/03/2025 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
Total | [13 empty] | 70.84 | 16.09 | 22.71