## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Laskarpur water supply scheme, T.W. No.- IV, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/001018/2023-2024 | 3879/ED | 06/10/2023 | 04/01/2024 | GHOSH AND GHOSH | 10.74 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Connection with 4th Tubewell to existing Laying Distribution Pipeline & Allied work for Laskarpur PWSS at JBpur Block of Howrah Sadar Sub Division under Howrah Division,P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000034/2024-2025 | 643/HSSD | 26/06/2024 | 26/07/2024 | ADRIJA ENTERPRISE | 4.9 | 0 | 0 | 100
3 | HOWRAH |  | Electrical | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Quotation money deposition for new service connection at Laskarpur w/s scheme, Zone- T.W. No.-VI, Dist.-Howrah under PHE Dte. Application No- 1007900745 Reference ID- 106654843 SM Code- 18842 |  |  | BILL/01273/2024-2025 | 332 | 30/07/2024 | 30/07/2024 | WBSEDCL | 23.11 | 0 | 0 | 0
4 | HOWRAH |  | Electrical | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Quotation money deposition for new service connection at Laskarpur w/s scheme, T.W. No.-V, Dist.-Howrah under PHE Dte. Application No- 1007772477 Reference ID- 106595815 SM Code- 18842 |  |  | BILL/01147/2024-2025 | 269 | 08/07/2024 | 08/07/2024 | WBSEDCL | 19.44 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method, connection with distribution system and Reconnection of FHTC & Allied Works, Construction of 2 (Two) Nos.Pump House (5.40m x 3.60m), Construction of 2 (Two) nos. Boundary Wall at Laskarpur Piped Water Supply Scheme Under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000576/2023-2024 | 966/HD | 28/02/2024 | 21/08/2025 | M/S SUMAN SHIL | 102.48 | 0 | 0 | 80
6 | HOWRAH |  | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Construction of approach road and land Development of 4th tubewell site, Construction of 1(one) nos. boundary wall, Construction of 4th Pump House (5.40m x 3.60m) for Laskarpur PWSS at Jagatballavpur at Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR |  | ORD/000429/2024-2025 | 892/HD | 11/02/2025 | 28/03/2025 | ADRIJA ENTERPRISE | 13.66 | 0 | 0 | 0
Total | [13 empty] | 174.33 | 0 | 0