## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Laskarpur water supply scheme, T.W. No.- IV, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/001018/2023-2024 | 3879/ED | 06/10/2023 | 04/01/2024 | GHOSH AND GHOSH | 10.74 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Connection with 4th Tubewell to existing Laying Distribution Pipeline & Allied work for Laskarpur PWSS at JBpur Block of Howrah Sadar Sub Division under Howrah Division,P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000034/2024-2025 | 643/HSSD | 26/06/2024 | 26/07/2024 | ADRIJA ENTERPRISE | 4.9 | 4.88 | 99.61 | 100
3 | HOWRAH |  | Electrical | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Quotation money deposition for new service connection at Laskarpur w/s scheme, Zone- T.W. No.-VI, Dist.-Howrah under PHE Dte. Application No- 1007900745 Reference ID- 106654843 SM Code- 18842 |  |  | BILL/01273/2024-2025 | 332 | 30/07/2024 | 30/07/2024 | WBSEDCL | 23.11 | 0 | 0 | 0
4 | HOWRAH |  | Electrical | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Quotation money deposition for new service connection at Laskarpur w/s scheme, T.W. No.-V, Dist.-Howrah under PHE Dte. Application No- 1007772477 Reference ID- 106595815 SM Code- 18842 |  |  | BILL/01147/2024-2025 | 269 | 08/07/2024 | 08/07/2024 | WBSEDCL | 19.44 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Construction of approach road and land Development of 4th tubewell site, Construction of 1(one) nos. boundary wall, Construction of 4th Pump House (5.40m x 3.60m) for Laskarpur PWSS at Jagatballavpur at Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR |  | ORD/000429/2024-2025 | 892/HD | 11/02/2025 | 28/03/2025 | ADRIJA ENTERPRISE | 13.66 | 0 | 0 | 0
6 | HOWRAH |  | Electrical | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Laskarpur Piped Water Supply Scheme Block- Jagatballavpur District- Howrah under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001301/2023-2024 | 4534/ED | 23/11/2023 | 16/05/2025 | DIPALI CONSTRUCTION | 21.49 | 15.92 | 74.1 | 30
7 | HOWRAH |  | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Reconnection of FHTC& Allied Works at Laskarpur PWSS at Jagatballavpur Block under Howrah sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR | je_how_rws_jagat | ORD/000716/2023-2024 | 158/HSSD | 12/02/2024 | 12/04/2024 | MANIRUL ISLAM | 0.94 | 0 | 0 | 100
8 | HOWRAH |  | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Preparation of DPR for Source Augmentation for Laskarpur PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P. H. E. Dte. | AE/SADAR |  | ORD/001008/2024-2025 | 817/HSSD | 07/08/2024 | 22/08/2024 | APEX ENGINEERING | 0.77 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method, connection with distribution system and Reconnection of FHTC & Allied Works, Construction of 2 (Two) Nos.Pump House (5.40m x 3.60m), Construction of 2 (Two) nos. Boundary Wall at Laskarpur Piped Water Supply Scheme Under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000576/2023-2024 | 966/HD | 28/02/2024 | 19/11/2025 | M/S SUMAN SHIL | 102.48 | 27.44 | 26.78 | 80
10 | HOWRAH |  | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Source Augmentation of Gobindapur Piped Water Supply Scheme [SM/18843],Source Augmentation of Laskarpur Piped Water Supply Scheme [SM/18842], and Source Augmentation of Majhu Khetra Water Supply Scheme [SM/18841] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/000987/2024-2025 | 233-A/HSSD | 28/02/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
11 | HOWRAH |  | Howrah Division | Source Augmentation of Laskarpur Piped Water Supply Scheme | SM/18842 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Gobindapur PWSS [SM/18843], Laskarpur PWSS [SM/18842], and Majhu Khetra PWSS [SM/18841] of Jagatballavpur Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/000999/2024-2025 | 232/HSSD | 28/02/2025 | 15/03/2025 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
Total | [13 empty] | 199.25 | 48.24 | 24.21