## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Source Augmentation of Gobindapur Piped Water Supply Scheme | SM/18843 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gobindapur water supply scheme, T.W. No.- III, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001019/2023-2024 | 3880/ED | 06/10/2023 | 04/01/2024 | ANIK & CO. | 10.75 | 0 | 0 | 40
2 | HOWRAH |  | Electrical | Source Augmentation of Gobindapur Piped Water Supply Scheme | SM/18843 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Gobindapur Piped Water Supply Scheme Block- Jagatballavpur District- Howrah under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001302/2023-2024 | 4535/ED | 23/11/2023 | 21/02/2024 | P.K. ENGINEERING | 10.74 | 9.03 | 84.09 | 30
3 | HOWRAH |  | Howrah Division | Source Augmentation of Gobindapur Piped Water Supply Scheme | SM/18843 | Augmentation | Sinking 1No. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with 150mm. dia. PVC. Strainer of 30m. length having 250 mm dia. 60 m. long PVC housing pipe & 150mm dia. 150m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Gobindapur PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000588/2023-2024 | 996/HD | 01/03/2024 | 31/03/2024 | ACME CONSTRUCTION | 14.58 | 13.81 | 94.76 | 100
4 | HOWRAH |  | Howrah Division | Source Augmentation of Gobindapur Piped Water Supply Scheme | SM/18843 | Augmentation | Additional Pipline & connection with 3rd Tubewell to existing Laying Distribution Pipeline & Allied work for Gobindapur PWSS at JBpur Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000036/2024-2025 | 644/HSSD | 26/06/2024 | 26/07/2024 | ADRIJA ENTERPRISE | 5.42 | 5.38 | 99.42 | 100
5 | HOWRAH |  | Electrical | Source Augmentation of Gobindapur Piped Water Supply Scheme | SM/18843 | Augmentation | Quotation money deposition for new service connection at Gobindapur w/s scheme, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1007622411 Reference ID- 106532178 SM Code- 18843 |  |  | BILL/00149/2024-2025 | 54 | 12/04/2024 | 12/04/2024 | WBSEDCL | 10.89 | 0 | 0 | 0
6 | HOWRAH |  | Electrical | Source Augmentation of Gobindapur Piped Water Supply Scheme | SM/18843 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gobindapur water supply scheme, T.W. No.- I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001020/2023-2024 | 3881/ED | 06/10/2023 | 04/01/2024 | OSMAN SEKH | 10.75 | 0 | 0 | 60
7 | HOWRAH |  | Howrah Division | Source Augmentation of Gobindapur Piped Water Supply Scheme | SM/18843 | Augmentation | Construction of approach road and land Development of 3rd tubewell site, Construction of 1(one) nos. boundary wall, Construction of 3rd Pump House (5.40m x 3.60m) for Gobindapur PWSS at Jagatballavpur at Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR |  | ORD/000430/2024-2025 | 893/HD | 11/02/2025 | 28/03/2025 | ADRIJA ENTERPRISE | 13.76 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Source Augmentation of Gobindapur Piped Water Supply Scheme | SM/18843 | Augmentation | Connection with distribution system and Reconnection of FHTC & allied Works, Construction of 1(One) No Pump House (5.40m x 3.60 m), Construction of 1(One) no Boundary Wall at Gobindapur Piped Water Supply Scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000595/2023-2024 | 1000/HD | 01/03/2024 | 26/12/2024 | LAKSHMI IRON | 59.38 | 37.26 | 62.74 | 10
9 | HOWRAH |  | Howrah Division | Source Augmentation of Gobindapur Piped Water Supply Scheme | SM/18843 | Augmentation | Reconnection of FHTC& Allied Works at Gabindapur PWSS at Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR | je_how_rws_jagat | ORD/000717/2023-2024 | 159/HSSD | 12/02/2024 | 12/04/2024 | MANIRUL ISLAM | 0.92 | 0 | 0 | 100
10 | HOWRAH |  | Howrah Division | Source Augmentation of Gobindapur Piped Water Supply Scheme | SM/18843 | Augmentation | Sinking 1 no. 250 X 150 mm dia and 240 m Replacement deep tube well drilling by direct rotary method with 150 mm. dia. PVC. strainer of 30 m. length having 250 mm dia. 60 m. long PVC housing pipe & 150 mm dia. 150 m. long well pipe alongwith 3m blank pipe all complete including cost of materials for Gobindapur PWSS at Jagatballavpur Block under Howrah Sadar Sub-Division under Howrah Division, P.H.E. Dte.. | AE/SADAR | je_how_rws_jagat | ORD/000072/2025-2026 | 2682/HD | 05/06/2025 | 01/05/2026 | AQUATECH ENGINEERS | 14.53 | 0 | 0 | 100
Total | [13 empty] | 151.71 | 65.49 | 43.17