## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Sahapur Piped Water Supply Scheme Block- Panchla District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001303/2023-2024 | 4536/ED | 23/11/2023 | 21/02/2024 | MUKHERJEE ART CENTRE | 10.68 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. from existing distributin system of Sahapur piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) | AE/SADAR |  | ORD/000423/2021-2022 | 337/HD | 17/02/2022 | 19/03/2022 | UNIVERSAL CONSTRUCTION | 2.98 | 1.31 | 43.95 | 100
3 | HOWRAH |  | Electrical | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Quotation money deposition for new service connection at Sahapur w/s scheme, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008116886 Reference ID- 106763473 SM Code- 18844 |  |  | BILL/02025/2024-2025 | 474 | 01/10/2024 | 01/10/2024 | WBSEDCL | 5.78 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Connection with distribution system and reconnection of FHTC & allied works, construction of 1 (One) no.pump house (5.40m x 3.60m),construction of 1 (One) no. boundary wall at Sahapur piped water supply scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000602/2023-2024 | 1067/HD | 04/03/2024 | 03/05/2024 | ADITYA HAZRA | 50.59 | 0 | 0 | 30
5 | HOWRAH |  | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Sinking 1No. 250 X 150 mm Dia and 240 m deep tube well drilling by direct rotary method with 150 mm. dia. PVC. strainer of 30m. length having 250 mm dia. 60m. long PVC housing pipe & 150 mm dia. 150m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Sahapur PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000591/2023-2024 | 1009/HD | 01/03/2024 | 26/11/2024 | AUXILIARY TUBEWELL DRILLERS | 14.59 | 0 | 0 | 100
6 | HOWRAH |  | Electrical | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Shifting of oh line along with dp installed for placing DTR for PHE at village Sahapur under Burikhali CCC. Application No- 100000126832 Reference ID- 860322112 SM Code- 18844 |  |  | BILL/02901/2024-2025 | 668 | 21/01/2025 | 21/01/2025 | WBSEDCL | 0.48 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Preparation of DPR for Source Augmentation for Sahapur PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P. H. E. Dte. | AE/SADAR |  | ORD/001009/2024-2025 | 826/HSSD | 09/08/2024 | 24/08/2024 | APEX ENGINEERING | 0.78 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Design,drawing, construction including rcc foundation and commissioning of iron elimination plant of capacity 50.00 cum per hours including 3(three) month trial run in the premises, construction of 3.60m X 3.00m size Blower room of compressure for IEP, at Sahapur PWSS Under Howrah Sadar Sub-Division of Howrah division P.H.E Dte. | AE/SADAR | je_how_rws_jagat | ORD/000050/2024-2025 | 2890/HD | 25/06/2024 | 17/12/2025 | NEER UDYOG | 24.38 | 0 | 0 | 100
9 | HOWRAH |  | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Sahapur PWSS [SM/18844], and Beldubi PWSS [SM/04274] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/000998/2024-2025 | 230/HSSD | 28/02/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 0.57 | 0 | 0 | 100
10 | HOWRAH |  | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Source Augmentation of Beldubi Water Supply Scheme [SM/18845], Source Augmentation of Bikihakola Water Supply Scheme [SM/18846], Source Augmentation of Sahapur Piped Water Supply Scheme [SM/18844] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/001000/2024-2025 | 233/HSSD | 28/02/2025 | 15/03/2025 | JHARNA ENTERPRISE | 0.85 | 0 | 0 | 100
Total | [13 empty] | 111.68 | 1.31 | 1.17