## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Sahapur Piped Water Supply Scheme Block- Panchla District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001303/2023-2024 | 4536/ED | 23/11/2023 | 21/02/2024 | MUKHERJEE ART CENTRE | 10.68 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. from existing distributin system of Sahapur piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) | AE/SADAR |  | ORD/000423/2021-2022 | 337/HD | 17/02/2022 | 19/03/2022 | UNIVERSAL CONSTRUCTION | 2.98 | 1.31 | 43.95 | 100
3 | HOWRAH |  | Electrical | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Quotation money deposition for new service connection at Sahapur w/s scheme, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008116886 Reference ID- 106763473 SM Code- 18844 |  |  | BILL/02025/2024-2025 | 474 | 01/10/2024 | 01/10/2024 | WBSEDCL | 5.78 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Connection with distribution system and reconnection of FHTC & allied works, construction of 1 (One) no.pump house (5.40m x 3.60m),construction of 1 (One) no. boundary wall at Sahapur piped water supply scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000602/2023-2024 | 1067/HD | 04/03/2024 | 03/05/2024 | ADITYA HAZRA | 50.59 | 0 | 0 | 30
5 | HOWRAH |  | Howrah Division | Source Augmentation of Sahapur Piped Water Supply Scheme | SM/18844 | Augmentation | Sinking 1No. 250 X 150 mm Dia and 240 m deep tube well drilling by direct rotary method with 150 mm. dia. PVC. strainer of 30m. length having 250 mm dia. 60m. long PVC housing pipe & 150 mm dia. 150m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Sahapur PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000591/2023-2024 | 1009/HD | 01/03/2024 | 26/11/2024 | AUXILIARY TUBEWELL DRILLERS | 14.59 | 0 | 0 | 100
Total | [13 empty] | 84.62 | 1.31 | 1.55