## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Source Augmentation of Beldubi Water Supply Scheme | SM/18845 | Augmentation | Sinking 1No. 250 X 150 mm Dia and 240 m deep tube well drilling by direct rotary method with 150 mm. dia. PVC. strainer of 30m. length having 250 mm dia. 60 m. long PVC housing pipe & 150 mm dia. 150 m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Beldubi PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000589/2023-2024 | 997/HD | 01/03/2024 | 31/03/2024 | AUXILIARY TUBEWELL DRILLERS | 14.59 | 0 | 0 | 100
2 | HOWRAH |  | Electrical | Source Augmentation of Beldubi Water Supply Scheme | SM/18845 | Augmentation | Quotation money deposition for new service connection at Beldubi w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008188704 Reference ID- 106812203 SM Code- 18845 |  |  | BILL/02272/2024-2025 | BP-24-25-583 | 19/11/2024 | 19/11/2024 | WBSEDCL | 4.19 | 0 | 0 | 0
3 | HOWRAH |  | Electrical | Source Augmentation of Beldubi Water Supply Scheme | SM/18845 | Augmentation | Quotation money deposition for additional work at Beldubi w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 100000124155 Reference ID- 860319335 SM Code- 18845 |  |  | BILL/02531/2024-2025 | 610 | 05/12/2024 | 05/12/2024 | WBSEDCL | 0.02 | 0 | 0 | 0
4 | HOWRAH |  | Electrical | Source Augmentation of Beldubi Water Supply Scheme | SM/18845 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Beldubi Water Supply Scheme Block- Panchla District- Howrah under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001304/2023-2024 | 4537/ED | 23/11/2023 | 30/05/2025 | D. K. ELECTRIC | 10.74 | 0 | 0 | 95
5 | HOWRAH |  | Howrah Division | Source Augmentation of Beldubi Water Supply Scheme | SM/18845 | Augmentation | Reconnection of FHTC & distribution pipe line and allied works, Construction of 1 (One) no.pump house (5.40m x 3.60 m), Construction of 1 (One) no. Boundary wall at Beldubi piped water supply scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000620/2023-2024 | 1139/HD | 06/03/2024 | 02/03/2025 | BISWAJIT BAG | 50.57 | 29.53 | 58.39 | 40
6 | HOWRAH |  | Howrah Division | Source Augmentation of Beldubi Water Supply Scheme | SM/18845 | Augmentation | Reconnection of FHTC& Allied Works at Beldubi PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR | JE/RWS/Panchla,je_how_rws_jagat | ORD/000719/2023-2024 | 161/HSSD | 12/02/2024 | 12/04/2024 | KUNAL BANERJEE | 0.9 | 0 | 0 | 100
Total | [13 empty] | 81.02 | 29.53 | 36.45