## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Source Augmentation of Beldubi Water Supply Scheme | SM/18845 | Augmentation | Sinking 1No. 250 X 150 mm Dia and 240 m deep tube well drilling by direct rotary method with 150 mm. dia. PVC. strainer of 30m. length having 250 mm dia. 60 m. long PVC housing pipe & 150 mm dia. 150 m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Beldubi PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000589/2023-2024 | 997/HD | 01/03/2024 | 31/03/2024 | AUXILIARY TUBEWELL DRILLERS | 14.59 | 0 | 0 | 100
2 | HOWRAH |  | Electrical | Source Augmentation of Beldubi Water Supply Scheme | SM/18845 | Augmentation | Quotation money deposition for new service connection at Beldubi w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008188704 Reference ID- 106812203 SM Code- 18845 |  |  | BILL/02272/2024-2025 | BP-24-25-583 | 19/11/2024 | 19/11/2024 | WBSEDCL | 4.19 | 0 | 0 | 0
3 | HOWRAH |  | Electrical | Source Augmentation of Beldubi Water Supply Scheme | SM/18845 | Augmentation | Quotation money deposition for additional work at Beldubi w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 100000124155 Reference ID- 860319335 SM Code- 18845 |  |  | BILL/02531/2024-2025 | 610 | 05/12/2024 | 05/12/2024 | WBSEDCL | 0.02 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Source Augmentation of Beldubi Water Supply Scheme | SM/18845 | Augmentation | Design,drawing,construction including rcc foundation and commissioning of iron elimination plant of capacity 50.00 cum per hour including 3(three) month trial run in the premises of Beldubi PWSS Under Howrah Sadar Sub-Division of Howrah Division P.H.E Dte. | AE/SADAR | je_how_rws_jagat | ORD/000048/2024-2025 | 2889/HD | 25/06/2024 | 18/09/2025 | NEER UDYOG | 24.38 | 0 | 0 | 0
Total | [13 empty] | 43.19 | 0 | 0