## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme | SM/18846 | Augmentation | Work Order Retrofitting work of Laying Pipeline From Node Point 4-162, 162-220 for Bikihakola PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | AE/SADAR |  | ORD/000596/2022-2023 | 2606/HD | 07/12/2022 | 21/01/2023 | UNIVERSAL CORPORATION | 11.28 | 5.71 | 50.64 | 40
2 | HOWRAH |  | Electrical | Source Augmentation of Bikihakola Water Supply Scheme | SM/18846 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Bikihakola Water Supply Scheme Block- Panchla District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001305/2023-2024 | 4538/ED | 23/11/2023 | 21/02/2024 | D. K. ELECTRIC | 10.74 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme | SM/18846 | Augmentation | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) | AE/SADAR |  | ORD/000495/2020-2021 | 425/HD | 11/02/2021 | 13/03/2021 | G.B. CONSTRUCTION AND CO | 92.5 | 17.93 | 19.38 | 100
4 | HOWRAH |  | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme | SM/18846 | Augmentation | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributin system of Bikihakola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) | AE/SADAR |  | ORD/000492/2020-2021 | 399/HD | 10/02/2021 | 12/03/2021 | M/S ASHIRBAD (INDIA) | 92.07 | 33.36 | 36.23 | 100
5 | HOWRAH |  | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme | SM/18846 | Augmentation | Work Order for Retrofitting work for Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola PWSS under Panchla Block of Howrah Sadar Sub Division under Howrah Division, PHE Dte.(Phase-II) (Part-A) No of House Hold= 100 nos. | AE/SADAR |  | ORD/000545/2021-2022 | 661/HD | 23/03/2022 | 12/04/2022 | UNIQUE CONSTRUCTION | 3.82 | 3.35 | 87.82 | 100
6 | HOWRAH |  | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme | SM/18846 | Augmentation | Work Order for Retrofitting work for Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola PWSS under Panchla Block of Howrah Sadar Sub Division under Howrah Division, PHE Dte.(Phase-II) (Part-B)No of House Hold= 100 nos. | AE/SADAR |  | ORD/000546/2021-2022 | 662/HD | 23/03/2022 | 12/04/2022 | UNIQUE CONSTRUCTION | 3.67 | 2.61 | 70.96 | 100
7 | HOWRAH |  | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme | SM/18846 | Augmentation | Work Order for Survey & Collection of house hold details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system in Bikihakola Piped Water Supply Scheme under Howrah District. (Part-C) | AE/SADAR |  | ORD/000519/2021-2022 | 508/HD | 08/03/2022 | 23/03/2022 | G.B. CONSTRUCTION AND CO | 0.68 | 0.68 | 100 | 100
8 | HOWRAH |  | Howrah Division | Source Augmentation of Bikihakola Water Supply Scheme | SM/18846 | Augmentation | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method, Construction of 1 (One) Nos.Pump House (5.40m x 3.60 m), Construction of 1(One) nos. Boundary Wall,Construction of Boundary Wall at Head work Site of Size-(50.00 m x 40.00 m), Construction of 700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/8/2012) including Soil Investigation, Foundation Design & All pipe Connection and Reconnection of FHTC & distribution pipe line and Allied Works at Bikiakhola PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000552/2023-2024 | 879/HD | 23/02/2024 | 16/08/2025 | THE UNICON ENGINEERS | 289.03 | 0 | 0 | 20
Total | [13 empty] | 503.81 | 63.64 | 12.63