## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Source Augmentation of Nakubar Water Supply Scheme | SM/18847 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Nakubar Water Supply Scheme Block- Amta-II District- Howrah under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001306/2023-2024 | 4539/ED | 23/11/2023 | 31/03/2025 | DEY ENTERPRISE | 21.5 | 0 | 0 | 40
2 | HOWRAH |  | Howrah Division | Source Augmentation of Nakubar Water Supply Scheme | SM/18847 | Augmentation | Work Order for Sinking of 1 (one) no PVC big dia additional Tube well 250 mm x 150 mm dia of 240 mtr deep at Nakubar W/S scheme at Amta-II Block in Uluberia Sub-Division under Howrah Division P.H.E Dte. | AE/Ulu | JE/USD | ORD/000188/2022-2023 | 1513/HD | 22/07/2022 | 11/08/2022 | NADIA TUBEWELLS | 12.71 | 11.44 | 90.02 | 100
3 | HOWRAH |  | Electrical | Source Augmentation of Nakubar Water Supply Scheme | SM/18847 | Augmentation | Quotation money deposition for new service connection at Nakubar 3 w/s scheme, Dist.-Howrah under PHE Dte. Application No- 1007699722 Reference ID- 106569868 SM Code- 18847 |  |  | BILL/00513/2024-2025 | 176 | 30/05/2024 | 30/05/2024 | WBSEDCL | 9.56 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Source Augmentation of Nakubar Water Supply Scheme | SM/18847 | Augmentation | Work Order for Construction of switch room (3.60 m x 3.0 m) with water supply & sanitary arrangement at 3rd tube well site of Nakubar PWSS of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | AE/Ulu | JE/USD | ORD/000583/2022-2023 | 2600/HD | 07/12/2022 | 26/01/2025 | S.M. CONSTRUCTION | 4.7 | 0 | 0 | 100
Total | [13 empty] | 48.46 | 11.44 | 23.61