## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Source Augmentation of Chitnan Water Supply Scheme | SM/18848 | Augmentation | Quotation Bill for New Service Connection at Chitnan W/S. Sch. TW-III |  |  | BILL/04517/2023-2024 | 562 | 22/12/2023 | 22/12/2023 | WBSEDCL | 4.85 | 0 | 0 | 0
2 | HOWRAH |  | Electrical | Source Augmentation of Chitnan Water Supply Scheme | SM/18848 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chitnan water supply scheme, T.W. No. III, Block: Amta-II, District: Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer6 | ORD/002475/2023-2024 | 336/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 10.43 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Source Augmentation of Chitnan Water Supply Scheme | SM/18848 | Augmentation | Work Order for Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep additional tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Chitnan PWSS of Amta-II Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/BLK/amta2,JE/RWS/Amta II | ORD/000611/2022-2023 | 2750/HD | 16/12/2022 | 15/01/2023 | LOKENATH ENTERPRISES | 15.12 | 12.73 | 84.16 | 100
4 | HOWRAH |  | Howrah Division | Source Augmentation of Chitnan Water Supply Scheme | SM/18848 | Augmentation | Preparation of DPR for Source Strengthning at Chitnan PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE-USD,JE/BLK/amta2 | ORD/000640/2023-2024 | 494/AE/USD | 29/09/2023 | 29/10/2023 | APEX ENGINEERING | 0.78 | 0 | 0 | 100
5 | HOWRAH |  | Howrah Division | Source Augmentation of Chitnan Water Supply Scheme | SM/18848 | Augmentation | Inter connection and distribution pipe line, construction of boundary wall with two storied switch room (1 Nos.) (3.6 x 3.0) at 3rd Tube well site of Chitnan PWSS of Amta-II Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/BLK/amta2 | ORD/000042/2025-2026 | 2314/HD | 13/05/2025 | 11/08/2025 | LOKENATH ENTERPRISES | 30.25 | 0 | 0 | 100
Total | [13 empty] | 61.43 | 12.73 | 20.72