## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Source Augmentation of Garbhabanipur Water Supply Scheme | SM/18849 | Augmentation | Sinking of additonal 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Garbhabanipur PWSS SM/18849 of Udaynarayanpur Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000667/2023-2024 | 1306/HD | 14/03/2024 | 13/04/2024 | WESTERN WATER SUPPLY AGENCY | 14.87 | 14.4 | 96.79 | 100
2 | HOWRAH |  | Howrah Division | Source Augmentation of Garbhabanipur Water Supply Scheme | SM/18849 | Augmentation | Preparation of DPR for Source Strengthning at Garhbhabanipur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE-USD,JE/USD | ORD/000642/2023-2024 | 496/AE/USD | 29/09/2023 | 29/10/2023 | APEX ENGINEERING | 0.78 | 0.22 | 28.27 | 100
3 | HOWRAH |  | Electrical | Source Augmentation of Garbhabanipur Water Supply Scheme | SM/18849 | Augmentation | Additional Quotation for new service connection for source Augmentation of Garbhabanipur Water Supply Scheme, PH NO- III in the district Howrah under Electrical Division, PHE Dte. (SM/18849), Reference Id- 860319020, Application no- 100000123590 |  |  | BILL/02475/2024-2025 | 614 | 05/12/2024 | 05/12/2024 | WBSEDCL | 0.74 | 0 | 0 | 0
4 | HOWRAH |  | Electrical | Source Augmentation of Garbhabanipur Water Supply Scheme | SM/18849 | Augmentation | Quotation for new service connection for source Augmentation of Garbhabanipur Water Supply Scheme, PH NO- III in the district Howrah under Electrical Division, PHE Dte. (SM/18849), Reference Id- 106616115, Application no- 1007816541 |  |  | BILL/00710/2024-2025 | 212 | 11/06/2024 | 11/06/2024 | WBSEDCL | 11.44 | 0 | 0 | 0
5 | HOWRAH |  | Electrical | Source Augmentation of Garbhabanipur Water Supply Scheme | SM/18849 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF GARBHABANIPUR PIPED W/S SCHEME, T.W. No. III, Block: Udaynarayanpur, District - Howrah under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002508/2023-2024 | 424/ED | 29/02/2024 | 01/08/2025 | SMILE | 10.74 | 0 | 0 | 90
6 | HOWRAH |  | Howrah Division | Source Augmentation of Garbhabanipur Water Supply Scheme | SM/18849 | Augmentation | Additional laying distribution pipeline with FHTC at Garbhabanipur PWSS SM/18849 of Udaynarayanpur Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000072/2024-2025 | 3121/HD | 09/07/2024 | 05/05/2025 | TAPU SAHA | 62.11 | 0 | 0 | 70
7 | HOWRAH |  | Howrah Division | Source Augmentation of Garbhabanipur Water Supply Scheme | SM/18849 | Augmentation | Land Development at 3rd Tube well Site Source Augmentation of Garbhabanipur PWSS scheme under Udaynarayanpur Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000582/2024-2025 | 1699/AE/USD | 28/02/2025 | 15/03/2025 | BIBHUTI SHAW | 3.52 | 0 | 0 | 100
Total | [13 empty] | 104.2 | 14.62 | 14.03