## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Source Augmentation of Bauria Water Supply Scheme | SM/18850 | Augmentation | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at at 3rd tube well site of Bauria PWSS of Uluberia-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | AE/Ulu |  | ORD/000050/2023-2024 | 1841/HD | 02/05/2023 | 31/07/2023 | CREATION | 6.95 | 6.69 | 96.27 | 100
2 | HOWRAH |  | Howrah Division | Source Augmentation of Bauria Water Supply Scheme | SM/18850 | Augmentation | Work Order for Connection between 3rd TW with distribution pipeline to built up pressure for Bauria w/s scheme under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000049/2023-2024 | 1842/HD | 02/05/2023 | 01/07/2023 | PRADIP KUMAR JATI | 48.41 | 41.43 | 85.58 | 100
3 | HOWRAH |  | Howrah Division | Source Augmentation of Bauria Water Supply Scheme | SM/18850 | Augmentation | Preparation of DPR for Source Strengthning at Bauria PWSS, Uluberia-I Block under Uluberia Sub-Division of Howrah Division PHE Dte | AE/Ulu | JE-USD,JE/USD | ORD/000641/2023-2024 | 495/AE/USD | 29/09/2023 | 29/10/2023 | APEX ENGINEERING | 0.78 | 0 | 0 | 100
4 | HOWRAH |  | Howrah Division | Source Augmentation of Bauria Water Supply Scheme | SM/18850 | Augmentation | Work Order for construction of Guard wall cum boundary wall, Land Development, Barbed wire protection at HW site Site & allied works of Bauria W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000733/2022-2023 | 570/HD | 13/02/2023 | 30/03/2023 | MJA ENTERPRISE | 37.38 | 31.02 | 82.98 | 60
5 | HOWRAH |  | Electrical | Source Augmentation of Bauria Water Supply Scheme | SM/18850 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bauria water supply scheme, T.W. No. III, Block: Uluberia-I, District - Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001017/2023-2024 | 3878/ED | 06/10/2023 | 02/05/2024 | MAA KALI ENTERPRISE | 10.74 | 10.4 | 96.79 | 70
Total | [13 empty] | 104.26 | 89.54 | 85.88