## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Source Augmentaion of kulgacchi Water Supply Scheme | SM/18882 | Augmentation | Quotation Bill for New Service Connection at Kulgachia W/S. Sch. TW-IV |  |  | BILL/04120/2023-2024 | 409 | 09/11/2023 | 09/11/2023 | WBSEDCL | 4.35 | 0 | 0 | 0
2 | HOWRAH |  | Electrical | Source Augmentaion of kulgacchi Water Supply Scheme | SM/18882 | Augmentation | Quotation Bill for New Service Connection at Kulgachia W/S. Sch. TW-III |  |  | BILL/04248/2023-2024 | 421 | 10/11/2023 | 10/11/2023 | WBSEDCL | 29.37 | 0 | 0 | 0
3 | HOWRAH |  | Electrical | Source Augmentaion of kulgacchi Water Supply Scheme | SM/18882 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentaion of Kulgacchi Water Supply Scheme Block- Uluberia - I District- Howrah under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001297/2023-2024 | 4530/ED | 23/11/2023 | 21/02/2024 | D. K. ELECTRIC | 32.23 | 20.93 | 64.94 | 35
4 | HOWRAH |  | Howrah Division | Source Augmentaion of kulgacchi Water Supply Scheme | SM/18882 | Augmentation | Re-Laying distribution system (HDPE & DI) & Shifting HouseHold Connection(FHTC) at Kulgachi PWSS of Uluberia -I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000685/2023-2024 | 3240/AE/USD | 12/03/2024 | 26/04/2024 | PRADIP KUMAR JATI | 28.64 | 28.5 | 99.53 | 100
5 | HOWRAH |  | Howrah Division | Source Augmentaion of kulgacchi Water Supply Scheme | SM/18882 | Augmentation | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Uluberia-I block of Uluberia Sub Division under Howrah Division, P.H.E. Dte. | AE HQ | je_blk_ballyjag_how | ORD/000652/2023-2024 | 1211/HD | 11/03/2024 | 26/03/2024 | TRIMARV SOLUTIONS PRIVATE LIMITED | 1.85 | 1.85 | 100 | 100
6 | HOWRAH |  | Howrah Division | Source Augmentaion of kulgacchi Water Supply Scheme | SM/18882 | Augmentation | Additional Laying of pipeline in addition to providing FHTC Kulgachi PWSS of Uluberia-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000531/2023-2024 | 2039/AE/USD | 13/02/2024 | 14/03/2024 | MA DURGA ENTERPRISE | 6.05 | 6.05 | 100 | 100
7 | HOWRAH |  | Howrah Division | Source Augmentaion of kulgacchi Water Supply Scheme | SM/18882 | Augmentation | Sinking of additional 3 (three) Nos. 250 X 150 mm Dia and 250 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete for Kulgachi PWSS of Uluberia-I Block of Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000038/2024-2025 | 2860/HD | 24/06/2024 | 23/08/2024 | G.T.AGRO CENTRE | 46.21 | 43.4 | 93.92 | 100
Total | [13 empty] | 148.69 | 100.73 | 67.74