## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Source Augmentation of Amragari Water Supply Scheme | SM/18883 | Augmentation | Construction of Remaining of 550 cum capacity, 20 mtr. staging height Over Head Reservoir including all allied works as per Departmental drawing at Amragori W/S Scheme under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/001295/2020-2021 | 542/HD | 15/06/2020 | 13/09/2020 | UNIQUE AGENCY | 31.5 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Source Augmentation of Amragari Water Supply Scheme | SM/18883 | Augmentation | Preparation of DPR for Source Strengthening at Amragori PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000460/2023-2024 | 826/AE/USD | 08/12/2023 | 07/01/2024 | APEX ENGINEERING | 2.76 | 0 | 0 | 0
3 | HOWRAH |  | Electrical | Source Augmentation of Amragari Water Supply Scheme | SM/18883 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Amragori water supply scheme, T.W. No. III, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002780/2022-2023 | 1796/ED | 02/11/2022 | 31/01/2023 | MENAKA ENTERPRISE | 10.84 | 10.81 | 99.77 | 100
4 | HOWRAH |  | Howrah Division | Source Augmentation of Amragari Water Supply Scheme | SM/18883 | Augmentation | Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Amragori PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (SM/18883) | AE/Ulu | JE/USD | ORD/000674/2023-2024 | 1311/HD | 14/03/2024 | 13/05/2024 | DEV DAS SHAW | 29.68 | 28.38 | 95.61 | 100
5 | HOWRAH |  | Electrical | Source Augmentation of Amragari Water Supply Scheme | SM/18883 | Augmentation | Quotation money deposition for new service connection at Amoragori w/s scheme, T.W. No.-V, Dist.-Howrah under PHE Dte. Application No- 1008024188 Reference ID- 106715771 SM Code- 18883 |  |  | BILL/02129/2024-2025 | 566 | 13/11/2024 | 13/11/2024 | WBSEDCL | 10.4 | 0 | 0 | 0
6 | HOWRAH |  | Electrical | Source Augmentation of Amragari Water Supply Scheme | SM/18883 | Augmentation | Quotation money deposition for new service connection at Amoragori w/s scheme, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1008024177 Reference ID- 106715773 SM Code- 18883 |  |  | BILL/02125/2024-2025 | 565 | 13/11/2024 | 13/11/2024 | WBSEDCL | 11.33 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Source Augmentation of Amragari Water Supply Scheme | SM/18883 | Augmentation | Construction of boundary wall with approach road at 3rd Site of Amragori PWSS in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000659/2023-2024 | 1299/HD | 13/03/2024 | 07/05/2025 | MANAS MALICK | 8.25 | 0 | 0 | 100
8 | HOWRAH |  | Howrah Division | Source Augmentation of Amragari Water Supply Scheme | SM/18883 | Augmentation | Laying distribution pipeline with FHTC at Amragori PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (SM/18883) | AE/Ulu | JE/USD | ORD/000079/2024-2025 | 3323/HD | 24/07/2024 | 17/09/2025 | MODERN CONSTRUCTION | 136.25 | 0 | 0 | 75
9 | HOWRAH |  | Electrical | Source Augmentation of Amragari Water Supply Scheme | SM/18883 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Amragari Water Supply Scheme Block- Amta-II District- Howrah under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001298/2023-2024 | 4531/ED | 23/11/2023 | 11/07/2025 | DAS ENTERPRISE | 21.49 | 15.91 | 74.05 | 40
10 | HOWRAH |  | Howrah Division | Source Augmentation of Amragari Water Supply Scheme | SM/18883 | Augmentation | Construction of 2nos switch room (5.4x 3.6) at TW site at Amragori PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (SM/18883) | AE/Ulu | JE/USD | ORD/000070/2024-2025 | 3120/HD | 09/07/2024 | 05/05/2025 | S S CONSTRUCTION | 12.56 | 0 | 0 | 100
11 | HOWRAH |  | Howrah Division | Source Augmentation of Amragari Water Supply Scheme | SM/18883 | Augmentation | Connection between 3rd TW with delivery pipeline, special repairing and allied works at Amragori PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E.Dte. | AE/Ulu | JE/USD | ORD/000150/2024-2025 | 698/AE/USD | 27/08/2024 | 21/09/2024 | DEV DAS SHAW | 2.88 | 0.74 | 25.83 | 100
12 | HOWRAH |  | Howrah Division | Source Augmentation of Amragari Water Supply Scheme | SM/18883 | Augmentation | Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep Tube Well by Drilling by Direct Rotary method with UPVC Pipes all complete under Source Augmentation of Amragori PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000346/2024-2025 | 5289/HD | 17/12/2024 | 15/02/2025 | G.T.AGRO CENTRE | 14.55 | 0 | 0 | 100
13 | HOWRAH |  | Electrical | Source Augmentation of Amragari Water Supply Scheme | SM/18883 | Augmentation | Shifting of Ltoh line near Amoragori 4 PHE Application No- 100000128110 Reference ID- 860323060 SM Code- 18883 |  |  | BILL/03083/2024-2025 | 694 | 31/01/2025 | 31/01/2025 | WBSEDCL | 0.38 | 0 | 0 | 0
Total | [13 empty] | 292.87 | 55.85 | 19.07