## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Source Augmentation of Sarda Water Supply Scheme | SM/18884 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Sarda Water Supply Scheme Block- Amta-II District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001299/2023-2024 | 4532/ED | 23/11/2023 | 21/02/2024 | S.B.ENTERPRISE | 10.74 | 0 | 0 | 0
2 | HOWRAH |  | Electrical | Source Augmentation of Sarda Water Supply Scheme | SM/18884 | Augmentation | Supply delivery and installation of Chlorinator for Sarda w/s scheme PH No. IV District Howrah under Electrical Division, PHE dte. |  |  | ORD/002568/2022-2023 | 721/HMSD | 23/03/2023 | 30/03/2023 | TRIO CONCERN | 0.8 | 0 | 0 | 100
3 | HOWRAH |  | Howrah Division | Source Augmentation of Sarda Water Supply Scheme | SM/18884 | Augmentation | Additional construction of 1nos switch room (5.4x 3.6) at TW site at Sarda PWSS SM/18884 of Amta-II Block in Uluberia Sub Division, under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000057/2024-2025 | 2911/HD | 26/06/2024 | 26/07/2024 | RANI CONSTRUCTION | 6.28 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Source Augmentation of Sarda Water Supply Scheme | SM/18884 | Augmentation | Preparation of DPR for Source Strengthning at Sarda PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE-USD,JE/USD | ORD/000682/2023-2024 | 517/AE/USD | 05/10/2023 | 04/11/2023 | APEX TECHNOLOGIES | 0.78 | 0 | 0 | 100
5 | HOWRAH |  | Howrah Division | Source Augmentation of Sarda Water Supply Scheme | SM/18884 | Augmentation | Additional laying distribution pipeline with FHTC at Sarda PWSS SM/18884 of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/BLK/amta2 | ORD/000045/2024-2025 | 2901/HD | 26/06/2024 | 19/09/2025 | S.S. ENTERPRISE | 43.21 | 0 | 0 | 45
Total | [13 empty] | 61.82 | 0 | 0