## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Source Augmentation of Balichak Water Supply Scheme | SM/18885 | Augmentation | Additional Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Balichack PWSS SM/18885 of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000666/2023-2024 | 1305/HD | 14/03/2024 | 13/05/2024 | ACME CONSTRUCTION | 29.98 | 28.06 | 93.57 | 100
2 | HOWRAH |  | Electrical | Source Augmentation of Balichak Water Supply Scheme | SM/18885 | Augmentation | Quotation money deposition for new service connection at Ballychak(Khalrah High School) w/s scheme, T.W. No.-VI, Dist.-Howrah under PHE Dte. Application No- 1008185087 Reference ID- 106811234 SM Code- 18885 |  |  | BILL/02274/2024-2025 | BP-24-25-580 | 19/11/2024 | 19/11/2024 | WBSEDCL | 25.61 | 0 | 0 | 0
3 | HOWRAH |  | Electrical | Source Augmentation of Balichak Water Supply Scheme | SM/18885 | Augmentation | Quotation money deposition for new service connection at Balichak w/s scheme, T.W. No.-V, Dist.-Howrah under PHE Dte. Application No- 1007772492 Reference ID- 106595796 SM Code- 18885 |  |  | BILL/00491/2024-2025 | 164 | 28/05/2024 | 28/05/2024 | WBSEDCL | 5.63 | 0 | 0 | 0
4 | HOWRAH |  | Electrical | Source Augmentation of Balichak Water Supply Scheme | SM/18885 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Balichak Water Supply Scheme Block- Amta-I District- Howrah under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001300/2023-2024 | 4533/ED | 23/11/2023 | 16/06/2025 | GHOSE ENGINEERING SYNDICATE | 21.91 | 0 | 0 | 50
5 | HOWRAH |  | Howrah Division | Source Augmentation of Balichak Water Supply Scheme | SM/18885 | Augmentation | Additional laying distribution pipeline with FHTC at Balichack PWSS SM/18885 of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000074/2024-2025 | 3164/HD | 12/07/2024 | 05/09/2025 | RANA ENTERPRISE | 34.95 | 0 | 0 | 100
6 | HOWRAH |  | Howrah Division | Source Augmentation of Balichak Water Supply Scheme | SM/18885 | Augmentation | Additional construction of 1nos switch room (5.4x 3.6) at 4th TW site and laying distribution pipeline with FHTC at Balichack PWSS SM/18885 of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000056/2024-2025 | 2858/HD | 24/06/2024 | 20/01/2025 | RANI CONSTRUCTION | 6.28 | 0 | 0 | 100
7 | HOWRAH |  | Howrah Division | Source Augmentation of Balichak Water Supply Scheme | SM/18885 | Augmentation | Additional construction of 1nos switch room (5.4x 3.6) at 5th TW site and laying distribution pipeline with FHTC at Balichack PWSS SM/18885 of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000075/2024-2025 | 3165/HD | 12/07/2024 | 03/01/2026 | ARUSHI CONSTRUCTION | 6.28 | 0 | 0 | 100
Total | [13 empty] | 130.64 | 28.06 | 21.48