## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Udaynarayanpur | Howrah Division | Uttar Manasri Piped Water Supply Scheme. | SM/18914 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 4024/HD | 07/11/2023 | 07/11/2023 | Resource Division | 116.49 | 0 | 0 | 0
2 | HOWRAH | Udaynarayanpur | Howrah Division | Uttar Manasri Piped Water Supply Scheme. | SM/18914 | New | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 1049/HD | 04/03/2024 | 04/03/2024 | Resource Division | 36.78 | 0 | 0 | 0
3 | HOWRAH | Udaynarayanpur | Howrah Division | Uttar Manasri Piped Water Supply Scheme. | SM/18914 | New | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 3884/HD | 05/09/2024 | 05/09/2024 | Resource Division | 9.98 | 0 | 0 | 0
4 | HOWRAH | Udaynarayanpur | Electrical | Uttar Manasri Piped Water Supply Scheme. | SM/18914 | New | Quotation Bill for New Service Connection at Uttar Manashree W/S. Sch. |  |  | BILL/05563/2023-2024 | 703 | 24/01/2024 | 24/01/2024 | WBSEDCL | 14.99 | 0 | 0 | 0
5 | HOWRAH | Udaynarayanpur | Electrical | Uttar Manasri Piped Water Supply Scheme. | SM/18914 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Uttar Manasri water supply scheme, T.W. No. I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001219/2023-2024 | 4542/ED | 23/11/2023 | 01/07/2025 | M/S DAS ENTERPRISE | 22.04 | 2.8 | 12.72 | 50
6 | HOWRAH | Udaynarayanpur | Howrah Division | Uttar Manasri Piped Water Supply Scheme. | SM/18914 | New | Construction of 600 cum capacity RCC OHR with 20.0 mtr. staging height including soil investigation, Sinking of 2 nos. 300 mm X 200 mm dia X 230 m deep Tubewell, Construction of 2 nos Switch Room with sanitary arrangement, Laying Distribution System, providing Functional Household Tap Connection (FHTC) for UTTAR MANASRI Piped Water Supply Scheme under Udaynarayanpur block under Howrah Division, PHE Dte. [No. of FHTC=3307] | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000261/2023-2024 | 3825/HD | 16/10/2023 | 03/04/2026 | SAMIRON GHOSH | 825.77 | 354.83 | 42.97 | 25
7 | HOWRAH | Udaynarayanpur | Howrah Division | Uttar Manasri Piped Water Supply Scheme. | SM/18914 | New | Construction of Boundary Wall, Land Development at HEAD WORK Site, Additional Laying of Distribution Pipe Lines at UTTAR MANASRI Piped Water Supply Scheme and Additional Laying of Distribution Pipe Lines at KHALATPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P. H. E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000012/2025-2026 | 1855/HD | 16/04/2025 | 10/02/2026 | SAMIRON GHOSH | 96.34 | 0 | 0 | 40
Total | [13 empty] | 1122.4 | 357.64 | 31.86