## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-II, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002386/2023-2024 | 3300/HMSD | 11/12/2023 | 10/06/2024 | DEBASHISH GHOSH | 0.86 | 0.15 | 17.03 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of drain using 1000 mm dia hume pipe and other allied works at Ichapur (Zone-12) of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer /DWSD I | je2_mont_hq | ORD/000632/2023-2024 | 1176/HD | 07/03/2024 | 22/03/2024 | SKYLINE ENTERPRISE | 0.96 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Pump House cum Guard room (5.5m x 3.6m) with Water Supply & Sanitary arrangement for Kalinagar PWSS at Purba Kalinagar (Janapara New Park) at Uluberia-I Block Of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | Assistant Engineer /DWSD I |  | ORD/000018/2024-2025 | 2692/HD | 10/06/2024 | 08/09/2024 | SUBRATA MONDAL | 7.65 | 0 | 0 | 0
4 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Hiring of Luxury Car (BS-IV) for the Official use of the Executive Engineer, Electrical Division, PHE Dte. w.e.f. 01.06.2024 to 30.11.2024. VEHICLE No. WB-02AB-3954 | Assistant Engineer 1 | Junior Engineer5 | ORD/000055/2024-2025 | 999/AE-I/ED | 16/05/2024 | 15/11/2024 | TRIDIP SARKAR | 0.87 | 2.39 | 275.38 | 0
5 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Shyampur-I & II Block of Uluberia Sub-Division under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000650/2023-2024 | 1209/HD | 11/03/2024 | 26/03/2024 | KULTIKARI MOTHER TERESA SOCIAL WELLFARE SOCIETY | 2.45 | 2.45 | 100 | 100
6 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of boundary wall at Manikpur H/W site (OHR 5A H/S) of Uluberia-I block of surface-based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | Assistant Engineer /DWSD I | je2_mont_hq | ORD/000537/2023-2024 | 739/HD | 16/02/2024 | 16/04/2024 | S R TRADING CORPORATION | 23.75 | 23.58 | 99.28 | 100
7 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Bullah piling for bank protection of canal to the right side of Ghat at Ichapur (Zone 12) for Surface Based W/S Scheme of Shyampur-I & II, Bagnan-I & II & Uluberia -I Block under of Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer /DWSD I | je2_mont_hq | ORD/000633/2023-2024 | 1177/HD | 07/03/2024 | 22/03/2024 | SKYLINE CONSTRUCTION | 0.96 | 0.93 | 97.17 | 100
8 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Approach Road (PHASE-1) at Nakol of surface based water supply scheme of Shyampur-I & II , Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | Assistant Engineer /DWSD I | je4_dgp | ORD/000042/2024-2025 | 2891/HD | 26/06/2024 | 26/07/2024 | KALIDAS ENTERPRISE | 4.61 | 4.58 | 99.38 | 100
9 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Approach Way at the premises of Camp Office Building of the Executive Engineer, Howrah Division of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer /DWSD I | je4_dgp | ORD/000071/2024-2025 | 3096/HD | 08/07/2024 | 07/08/2024 | K.N ENTERPRISE | 2.68 | 2.67 | 99.51 | 100
10 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Kiosk (one no)(Size inside 3.0 x 1.8m) for Kalinagar PWSS at Janapara & temporary approach way of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. (Size inside 3.0 x 1.8m) | AE/RWS | je4_dgp | ORD/000118/2024-2025 | 3786/HD | 02/09/2024 | 17/09/2024 | ZUNAID ENTERPRISE | 2.03 | 1.96 | 96.74 | 100
11 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of18 mtr boundary wall from the Bandh road (chainage 0 mtr to 18 mtr) upto the mid point of Right side of the Substation building at Kajiakhali of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer /DWSD I | je2_mont_hq | ORD/000081/2024-2025 | 3364/HD | 30/07/2024 | 13/09/2024 | RINKU SAU | 4.84 | 4.77 | 98.45 | 100
12 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Approach Road (PHASE-2) at Nakol of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | Assistant Engineer /DWSD I | je4_dgp | ORD/000051/2024-2025 | 2903/HD | 26/06/2024 | 11/07/2024 | KALIDAS ENTERPRISE | 5.72 | 5.63 | 98.45 | 100
13 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of boundary wall at Choto Joynagar tubewell site under Belari PWSS( Zone 13) of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer /DWSD I | je2_mont_hq | ORD/000052/2024-2025 | 2902/HD | 26/06/2024 | 10/08/2024 | KALIDAS ENTERPRISE | 9.71 | 9.69 | 99.84 | 100
14 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Temporary Approach Road at Kamardaha (Zone- 37) of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer /DWSD I | je4_dgp | ORD/000063/2024-2025 | 3094/HD | 08/07/2024 | 05/12/2024 | K.N ENTERPRISE | 5.1 | 4.92 | 96.48 | 100
15 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of boundary wall, Bank Protection at Dalsalap (Zone No. 03) (J.L No. 45) & Interconnection between Tubewell & Distribution Pipeline of Belari PWSS at Choto Jaynagar of Shyampur I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer /DWSD I | je4_dgp | ORD/000029/2024-2025 | 2841/HD | 21/06/2024 | 20/08/2024 | K.N ENTERPRISE | 40.28 | 37.54 | 93.2 | 100
16 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Slab Culvert for Kalinagar PWSS at Alipukur of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je4_dgp | ORD/000141/2024-2025 | 4115/HD | 23/09/2024 | 30/09/2024 | ZUNAID ENTERPRISE | 0.97 | 0.93 | 95.93 | 100
17 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Bullah piling for bank protection of canal to the left side of Ghat at Ichapur (Zone 12) for Surface Based W/S Scheme of Shyampur-I & II, Bagnan-I & II & Uluberia-I Block under of Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer /DWSD I | je2_mont_hq | ORD/000634/2023-2024 | 1178/HD | 07/03/2024 | 22/03/2024 | SKYLINE CONSTRUCTION | 0.96 | 0.93 | 97.04 | 100
18 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Supply & Delivery of different types of DI Specials for Surface Based W/S Scheme of Shyampur-I & II, Part of Bagnan-I & II & Uluberia-I Block Under Howrah Division, PHE Dte. | Assistant Engineer /DWSD I | je4_dgp | ORD/000023/2024-2025 | 2689/HD | 07/06/2024 | 22/06/2024 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 86.34 | 86.34 | 100 | 100
19 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of drain beside Dhoramanna khal (Zone No. 35) of Bagnan-II block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je4_dgp | ORD/000102/2024-2025 | 3543/HD | 09/08/2024 | 16/08/2024 | SIDDHARTH ENTERPRISE | 0.97 | 0.96 | 99.38 | 100
20 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Approach Road for Second H/W site of Baikhai PWSS under Uluberia-I block of Surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer /DWSD I | je2_mont_hq | ORD/000065/2024-2025 | 3095/HD | 08/07/2024 | 23/07/2024 | K.N ENTERPRISE | 2.57 | 2.51 | 97.57 | 100
21 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Approach Road for Kalinagar PWSS at Alipukur of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je4_dgp | ORD/000139/2024-2025 | 4113/HD | 23/09/2024 | 30/09/2024 | ZUNAID ENTERPRISE | 0.92 | 0.9 | 97.73 | 100
22 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Temporary Approach Road at Ghatampur (Zone- 4) of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je4_dgp | ORD/000140/2024-2025 | 4114/HD | 23/09/2024 | 30/09/2024 | RINKU SAU | 0.94 | 0.92 | 98.33 | 100
23 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Kiosk (one no) for Kalinagar PWSS at Alipukur of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte | AE/RWS | je4_dgp | ORD/000142/2024-2025 | 4116/HD | 23/09/2024 | 30/09/2024 | ZUNAID ENTERPRISE | 0.89 | 0.8 | 89.23 | 100
24 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Boundary wall at Moubeshia tubewell site under Baikhali PWSS(Zone-7) of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer /DWSD I | je2_mont_hq | ORD/000066/2024-2025 | 3097/HD | 08/07/2024 | 07/08/2024 | K.N ENTERPRISE | 9.7 | 9.68 | 99.76 | 100
25 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SHYAMPUR PIPED W/S SCHEME, Zone-I, T.W. No. I (Replacement), Block: Shyampur-I, District - Howrah under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000376/2024-2025 | 1463/ED | 25/07/2024 | 23/10/2024 | DIPALI CONSTRUCTION | 11.1 | 10.8 | 97.35 | 90
26 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Approach Road for alternate entrance of Camp office under Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je2_mont_hq | ORD/000103/2024-2025 | 3544/HD | 09/08/2024 | 16/08/2024 | SIDDHARTH ENTERPRISE | 0.97 | 0.96 | 99.41 | 100
27 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Rest Shed & Other Allied Works at Ghanashyampur (Zone 11) beside OHR site under Shyampur-II Block of Surface Based Water Supply Scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer /DWSD I | je2_mont_hq | ORD/000080/2024-2025 | 3324/HD | 24/07/2024 | 23/08/2024 | S R TRADING CORPORATION | 3.71 | 3.69 | 99.42 | 100
28 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of 18 mtr boundary wall (chainage 18 mtr to 36 mtr) from the midpoint & upto the end point of Right side of the Substation building at Kajiakhali of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer /DWSD I | je2_mont_hq | ORD/000082/2024-2025 | 3380/HD | 30/07/2024 | 13/09/2024 | RINKU SAU | 4.84 | 4.77 | 98.45 | 100
29 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2024-2025 | 5140/HD | 11/12/2024 | 11/12/2024 | Resource Division | 4159.12 | 0 | 0 | 0
30 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 4561/HD | 23/10/2024 | 23/10/2024 | Resource Division | 1803.32 | 0 | 0 | 0
31 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 4673/HD | 06/11/2024 | 06/11/2024 | Resource Division | 39.57 | 0 | 0 | 0
32 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. Car No. WB-19J-7094 From 01.06.2024 to 30.06.2024 |  |  | BILL/02056/2024-2025 | 514 | 21/10/2024 | 21/10/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.26 | 0 | 0 | 0
33 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. Car No.- WB-02AT-8617 01.08.2024 to 31.08.2024 |  |  | BILL/02270/2024-2025 | BP-24-25-589 | 19/11/2024 | 19/11/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.14 | 0 | 0 | 0
34 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. Car No. WB-19J-7094 From 01.07.2024 to 31.07.2024 |  |  | BILL/02055/2024-2025 | 515 | 21/10/2024 | 21/10/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
35 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. Car No.- WB-02AT-8617 01.06.2024 to 30.06.2024 |  |  | BILL/01821/2024-2025 | 450 | 10/09/2024 | 10/09/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0 | 0
36 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. Car No. WB-04G-2822 From 01.09.2024 to 30.09.2024 |  |  | BILL/02083/2024-2025 | 530 | 28/10/2024 | 28/10/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.17 | 0 | 0 | 0
37 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Quotation for new service connection in the district Howrah under Electrical Division, PHE Dte. ( SM/19186), Reference Id- 106776950 Application no- 1008136524 |  |  | BILL/02295/2024-2025 | BP-24-25-592 | 21/11/2024 | 21/11/2024 | WBSEDCL | 17.75 | 0 | 0 | 0
38 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks . App. No.-1008024203 Ref. ID.-106715772 SM/19186 |  |  | BILL/02131/2024-2025 | 568 | 13/11/2024 | 13/11/2024 | WBSEDCL | 10.03 | 0 | 0 | 0
39 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Quotation money deposition for new service connection Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, Dist.-Howrah under PHE Dte. Application No- 1008027751 Reference ID- 106717103 SM Code- 19186 |  |  | BILL/02115/2024-2025 | 555 | 05/11/2024 | 05/11/2024 | WBSEDCL | 14.39 | 0 | 0 | 0
40 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Quotation money deposition for new service connection Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, Dist.-Howrah under PHE Dte. Application No- 1008027768 Reference ID- 106717102 SM Code- 19186 |  |  | BILL/02114/2024-2025 | 554 | 05/11/2024 | 05/11/2024 | WBSEDCL | 14.39 | 0 | 0 | 0
41 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. Car No.- WB-02AT-8617 01.07.2024 to 31.07.2024 |  |  | BILL/01822/2024-2025 | BP-24-25-588 | 19/11/2024 | 19/11/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0 | 0
42 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. Car No.- WB-04G-2822 From - 01.09.2024 to 30.09.2024 |  |  | BILL/02082/2024-2025 | 528 | 28/10/2024 | 28/10/2024 | DASHRATH KUMAR PRAJAPATI | 0.07 | 0 | 0 | 0
43 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, P.H No.-IV of Amritsal. App. No.-1007859284 Ref. ID.-106635058 SM/19186 |  |  | BILL/00958/2024-2025 | 259 | 03/07/2024 | 03/07/2024 | WBSEDCL | 4.5 | 0 | 0 | 0
44 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. WB-04G-2822 01.08.2024 to 31.08.2024 |  |  | BILL/01994/2024-2025 | 470 | 01/10/2024 | 01/10/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.21 | 0 | 0 | 0
45 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks . App. No.-1007900847 Ref. ID.-106654842 SM/19186 |  |  | BILL/02130/2024-2025 | 569 | 13/11/2024 | 13/11/2024 | WBSEDCL | 24.34 | 0 | 0 | 0
46 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From:- 01/05/2024 to 31/05/2024 Bill No.- 0246 |  |  | BILL/02269/2024-2025 | BP-24-25-587 | 19/11/2024 | 19/11/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
47 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, P.H No.-III of Amritsal. App. No.-1007867663 SM/19186 |  |  | BILL/00965/2024-2025 | 258 | 03/07/2024 | 03/07/2024 | WBSEDCL | 3.82 | 0 | 0 | 0
48 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. WB-04G-2822 01/07/2024 to 31/07/2024 |  |  | BILL/01628/2024-2025 | 364 | 12/08/2024 | 12/08/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
49 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. Car No. WB-19J-7094 From 01.08.2024 to 31.08.2024 |  |  | BILL/02057/2024-2025 | 512 | 21/10/2024 | 21/10/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
50 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From:- 01/04/2024 to 30/04/2024 Bill No.- 0107 |  |  | BILL/02268/2024-2025 | BP-24-25-586 | 19/11/2024 | 19/11/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.26 | 0 | 0 | 0
51 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. Car No. WB-04G-2822 From 01/10/2024 to 31/10/2024 |  |  | BILL/02332/2024-2025 | 622 | 06/12/2024 | 06/12/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
52 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Quotation money deposition for new service connection Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, Dist.-Howrah under PHE Dte. Application No- 1007786607 Reference ID- 106603564 SM Code- 19186 |  |  | BILL/02119/2024-2025 | 553 | 05/11/2024 | 05/11/2024 | WBSEDCL | 9.85 | 0 | 0 | 0
53 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000283/2024-2025 | 1359/AE-I/ED | 21/06/2024 | 22/12/2024 | DASHRATH KUMAR PRAJAPATI | 0.87 | 0.73 | 83.15 | 0
54 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Hiring of 1(One) no. Inspection vehicle no-2 (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Surface Based Water Supply Scheme for "Shyampur", PHE Dte. Government of West Bengal(for the period from 13.10.2024 to 12.10.2025). | AE/RWS | je4_dgp | ORD/000259/2024-2025 | 4445/HD | 03/10/2024 | 03/10/2025 | MR SAP ENTERPRISE | 4.78 | 2.97 | 62.05 | 0
55 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Hiring of 1 (One) no. Inspection vehicle no-1 (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Surface Based Water Supply Scheme for "Shyampur", PHE Dte. Government of West Bengal (for the period from 13.10.2024 to 12.10.2025). | AE/RWS | je4_dgp | ORD/000258/2024-2025 | 4444/HD | 03/10/2024 | 03/10/2025 | M/S ANIMESH ENTERPRISE | 4.78 | 2.97 | 62 | 15
56 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of counterfort retaining wall at backend & left side of Substation building at Kajiakhali under Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je2_mont_hq | ORD/000173/2024-2025 | 4364/HD | 30/09/2024 | 25/09/2025 | S R TRADING CORPORATION | 32.44 | 0 | 0 | 5
57 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of boundary wall at Nakol H/W site of Shyampur-II block under Surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je2_mont_hq | ORD/000188/2024-2025 | 4462/HD | 03/10/2024 | 31/01/2025 | KALIDAS ENTERPRISE | 21.69 | 0 | 0 | 80
58 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of boundary wall and land development at Khalore H/W site (OHR 40A) under Bagnan-I block of Surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je2_mont_hq | ORD/000643/2024-2025 | 1248/HD | 06/03/2025 | 02/09/2025 | K.N ENTERPRISE | 16.57 | 0 | 0 | 75
59 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5 m) at Hallyan (Zone -29) at Bagnan¿II Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je4_dgp | ORD/000087/2025-2026 | 2801/HD | 17/06/2025 | 16/08/2025 | SIDDHARTH ENTERPRISE | 7.73 | 0 | 0 | 0
60 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5 m) at Ramchandrapur (Zone-40) at Bagnan¿I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je2_mont_hq | ORD/000088/2025-2026 | 2802/HD | 17/06/2025 | 13/04/2026 | K.N ENTERPRISE | 7.73 | 0 | 0 | 80
61 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5 m) at Kulgachia (Zone -5) at Uluberia¿I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je2_mont_hq | ORD/000069/2025-2026 | 2575/HD | 02/06/2025 | 29/11/2025 | S S CONSTRUCTION | 9.77 | 0 | 0 | 75
62 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of boundary wall, land development and other allied works at Amritashal (Zone No. 09) (J.L No. 38) of Uluberia I block of surface-based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je4_dgp | ORD/000551/2024-2025 | 1073/HD | 27/02/2025 | 27/06/2025 | SK. MOMTAJUR RAHAMAN | 26.59 | 0 | 0 | 78
63 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Extension of boundary wall and land development at Mugkalyan H/W site (OHR 32 & 32A) under Bagnan-II block of Surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je2_mont_hq | ORD/000459/2024-2025 | 991/HD | 20/02/2025 | 02/03/2026 | S R TRADING CORPORATION | 42.84 | 0 | 0 | 70
64 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of boundary wall at Barunda H/W site (Zone 38) of Bagnan-II block of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je2_mont_hq | ORD/000084/2025-2026 | 2663/HD | 05/06/2025 | 02/12/2025 | K.N ENTERPRISE | 24.86 | 0 | 0 | 75
65 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Shyampur-I & II Block) | AE HQ |  | ORD/000221/2025-2026 | 4119/HD | 14/10/2025 | 13/11/2025 | JHARNA ENTERPRISE | 4.79 | 0 | 0 | 0
66 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Uluberia-I Block) (PART-B) | AE HQ |  | ORD/000224/2025-2026 | 4122/HD | 14/10/2025 | 13/11/2025 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
67 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Interconnection between Tubewell & Distribution Pipeline of Kalinagar PWSS at Alipukur & Fencing at the front side of entry of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je4_dgp | ORD/000101/2024-2025 | 3542/HD | 09/08/2024 | 16/08/2024 | SIDDHARTH ENTERPRISE | 0.83 | 0.64 | 76.57 | 100
68 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of boundary wall, land development & other alied work for Kalinagar PWSS at Alipukur of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je4_dgp | ORD/000331/2024-2025 | 4876/HD | 25/11/2024 | 09/04/2025 | S.S CONSTRUCTION | 7.55 | 0 | 0 | 100
69 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Chakkamala Samsan Chulli beside Chakkamala OHR Site (Zone No.-35) of Bagnan-II block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je4_dgp | ORD/000110/2024-2025 | 3718/HD | 28/08/2024 | 25/01/2025 | S.S ENTERPRISE | 2.77 | 0 | 0 | 100
70 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Balance work of boundary wall at Manikpur H/W site (OHR 5A) of Uluberia-I Block under Surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je2_mont_hq | ORD/000336/2024-2025 | 4917/HD | 27/11/2024 | 26/05/2025 | S R TRADING CORPORATION | 17.03 | 0 | 0 | 100
71 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Plastering, Painting, Supplying, Fitting & fixing of iron post & Barbid wire at the Right Side Wall (Chainage 0 mtr to 36 mtr) of Substation Building at kajiakhali of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je2_mont_hq | ORD/000083/2024-2025 | 3363/HD | 30/07/2024 | 12/12/2024 | RINKU SAU | 1.27 | 0 | 0 | 100
72 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5 m) at Barberia (Zone -8) at Uluberia¿I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je2_mont_hq | ORD/000070/2025-2026 | 2576/HD | 02/06/2025 | 01/08/2025 | USHA CONCERN | 7.7 | 0 | 0 | 100
73 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5m) at Amritsal (Zone-9) at Uluberia¿ I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je4_dgp | ORD/000061/2025-2026 | 2500/HD | 26/05/2025 | 25/07/2025 | SK. MOMTAJUR RAHAMAN | 7.69 | 0 | 0 | 100
74 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Extension of boundary wall, land development and other allied works at Orphuli (Zone No. 34) of Bagnan-II block of Surface-based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS,AE/Ulu | je4_dgp | ORD/000458/2024-2025 | 990/HD | 20/02/2025 | 21/04/2025 | M/S MJA ENTERPRISE | 18.47 | 0 | 0 | 100
75 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Hume Pipe Culvert, Land development & Protection work at Mongrajpur(OHR 6) of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je4_dgp | ORD/000436/2024-2025 | 922/HD | 17/02/2025 | 03/04/2025 | SAIKAT ENTERPRISE | 7.5 | 0 | 0 | 100
76 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5 m) at Radhapur (Zone -19) at Shyampur¿ I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je2_mont_hq | ORD/000089/2025-2026 | 2803/HD | 17/06/2025 | 16/08/2025 | MARUTI CONSTRUCTION | 7.73 | 0 | 0 | 100
77 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Balance work for Construction of retaining Wall, drain and others allied works at Chakkamala of Bagnana II block of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je4_dgp | ORD/000083/2025-2026 | 2766/HD | 12/06/2025 | 12/07/2025 | S.S ENTERPRISE | 3.13 | 0 | 0 | 100
78 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2024-2025 | 985/HD | 20/02/2025 | 20/02/2025 | Resource Division | 770 | 0 | 0 | 0
79 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2025-2026 | 3961/HD | 22/09/2025 | 22/09/2025 | Resource Division | 967.61 | 0 | 0 | 0
80 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2025-2026 | 3621/HD | 28/08/2025 | 28/08/2025 | Resource Division | 34.87 | 0 | 0 | 0
81 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2025-2026 | 2177/HD | 30/04/2025 | 30/04/2025 | Resource Division | 56.64 | 0 | 0 | 0
82 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | New Connection of Electricity (WBSEDCL) for Camp office of Executive Engineer, Howrah Division PHE Dte for Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks. Application No- 1008331661 Reference ID- 106904440 SM Code- 19186 |  |  | BILL/03076/2024-2025 | 669 | 21/01/2025 | 21/01/2025 | WBSEDCL | 0.72 | 0 | 0 | 0
83 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Supply of Fuel for 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. (JJM Work for Hooghly District) for the Month of October 2024. |  |  | BILL/02701/2025-2026 |  | 09/09/2025 | 09/09/2025 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
84 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Upgradation of PMGSY road from MRL 07-Kalinagar (Maniktala Stoppage) to Hirapur under Uluberia-I Block in the district of Howrah |  |  | BILL/00009/2025-2026 |  | 07/04/2025 | 07/04/2025 | WBSRDA | 26.88 | 0 | 0 | 0
85 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. Car No. WB-04G-2822 Bill No. 1071 Bill Date: 30/11/2024 |  |  | BILL/02833/2024-2025 | 643 | 09/01/2025 | 09/01/2025 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
86 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Shifiting of LTOH LINE near OHR-III under Shyampur project Application No- 100000141270 Reference ID- 860340560 SM Code- 19186 |  |  | BILL/01217/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 0.64 | 0 | 0 | 0
87 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of OCTOBER,2024 |  |  | BILL/03117/2024-2025 |  | 29/01/2025 | 29/01/2025 | JAMECO AGENCIES PRIVATE LIMITED. | 0.08 | 0 | 0 | 0
88 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Surveying, Designing, Supplying, Laying & Commissioning of Distribution System for 28 nos Zones including construction of all pipe supporting structure & FHTC under Shyampur-I, II, & Part of Bagnan-I & II Block of Howrah District with 3 months trial run & Operation & Maintenance of all the works for a period of 3 (Three) years under Augmentation of Surface Based W/S scheme for Shyampur-I & II, Uluberia I and Part of Bagnan I & II Block ("Contract Package-3" as per detail scope of works.), District- Howrah | AE/RWS,Assistant Engineer /DWSD I | je/blk/shyam1,JE/RWS/Bagnan I,je2_mont_hq,je4_dgp | ORD/000622/2023-2024 | 1160/HD | 07/03/2024 | 01/01/2026 | WPIL LIMITED | 29388.95 | 0 | 0 | 15
89 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. (JJM Work for Hooghly District) | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000699/2024-2025 | 5589/HMSD | 27/09/2024 | 25/02/2025 | SANJIB PRADHAN | 0.72 | 0 | 0 | 0
90 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of boundary wall at Kamardaha (Zone No. 37) of Bagnan-II block of surface-based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS,AE/Ulu | je4_dgp | ORD/000014/2025-2026 | 1880/HD | 17/04/2025 | 16/06/2025 | S.S CONSTRUCTION | 26.72 | 0 | 0 | 0
91 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Hiring of 1 (One) no. Inspection vehicle no-3 (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Surface Based Water Supply Scheme for "Shyampur", PHE Dte. Government of West Bengal (for the period from 365 days) (w.e.f.,01/02/2025 to 31/01/2026) | AE/RWS | je4_dgp | ORD/000499/2024-2025 | 696/HD | 29/01/2025 | 29/01/2026 | BIJITA TRAVELS | 4.78 | 1.57 | 32.88 | 0
92 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Proposed Surface Based Water Supply Scheme for Part of Malancha Beria, Rauta, Harinarayanpur and Kaijuri of Uluberia I Block under "Surface Based Water Supply Scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block" [No. of FHTC=1723] (SM/19186) | AE/RWS | je4_dgp | ORD/000779/2024-2025 | 1488/HD | 20/03/2025 | 14/01/2026 | APRJ CONSTRUCTIONS | 707.58 | 0 | 0 | 0
93 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Additional Work of Laying Distribution system (LDS) & Road Restoration Work at Uluberia-1 & Shyampur-1 Block of Surface Based W/S scheme for Shyampur-I & II, Uluberia I and Part of Bagnan I & II Block under Howrah Division, PHE Dte. (SM/06386 & SM/19186) | AE/RWS | je2_mont_hq,je4_dgp | ORD/000454/2024-2025 | 994/HD | 20/02/2025 | 01/07/2026 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 1950.12 | 180.54 | 9.26 | 60
94 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Uluberia-I Block) (PART-A) | AE HQ |  | ORD/000223/2025-2026 | 4121/HD | 14/10/2025 | 13/11/2025 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
95 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Construction of Chlorine Room (5.5 m x 4.5 m) at Gouripur (Zone -1) at Uluberia¿ I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. | AE/RWS | je4_dgp | ORD/000101/2025-2026 | 3025/HD | 03/07/2025 | 31/10/2025 | BISWAJIT BAG | 7.74 | 0 | 0 | 100
96 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | PHE Restoration work of road from L026-T01 Mahamayatola to Tiorpara L026 Baikhali Bridge to Tiorpara Bridge via Palpara Madai at Dhulasimla, Hirapur GP under Ulubria-I block in the district of Howrah vide Pckg no. WB-09-303 |  |  | BILL/00240/2026-2027 |  | 26/05/2026 | 26/05/2026 | WBSRDA-II | 12.78 | 0 | 0 | 0
97 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | PHE Restoration work of road from L046-t06 Damodarpur to Paschimkalinagarkachari L046 at Bahira & Kalinagar GP under Uluberia-I block in the district of Howrah vide Pkg no-WB-09-209 |  |  | BILL/00241/2026-2027 |  | 26/05/2026 | 26/05/2026 | WBSRDA-II | 4.02 | 0 | 0 | 0
98 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | PHE Restoration work of road from T03 Uttar Konranrapara to Khalpara Daspara 1053 at Hatgachha-I GP under Uluberia-1 block in the district of Howrah. vide pkg no WB-09-204 |  |  | BILL/00243/2026-2027 |  | 26/05/2026 | 26/05/2026 | WBSRDA-II | 1.75 | 0 | 0 | 0
99 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Supply of Fuel of 1(One) no Diesel luxury Taxi on contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division PHE Dte(JJM work for Hooghly District) for the Month of December 2024 Car No-WB04H1945 |  |  | BILL/07051/2025-2026 |  | 25/02/2026 | 25/02/2026 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
100 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | PHE Restoration work of road from L043-L042 Khandarpara to Mahisalibagdipara L043 at Hatgachha-l, Bahira GP under Uluberia-I block in the district of Howrah. vide Pkg No- WB-09-203 |  |  | BILL/00244/2026-2027 |  | 26/05/2026 | 26/05/2026 | WBSRDA-II | 5.63 | 0 | 0 | 0
101 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | PHE Restoration work of road from L044-1043 Aymachandpur to Badakhal 1 L043 at Balichaturi GP under Shyampur-i block in the district of Howrah vide Pkg No-WB-09-270. |  |  | BILL/00250/2026-2027 |  | 26/05/2026 | 26/05/2026 | WBSRDA-II | 12.04 | 0 | 0 | 0
102 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Supply of Fuel of 1(One) no Diesel luxury Taxi on contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division PHE Dte(JJM work for Hooghly District) for the Month of November 2024. Car No-WB04H 1945. |  |  | BILL/07052/2025-2026 |  | 25/02/2026 | 25/02/2026 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
103 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Repair of L030-L027 Mirpara to Ayma Hallyan L030 road damaged by PHE Dept. Package No. WB-09-240 |  |  | BILL/00245/2026-2027 |  | 26/05/2026 | 26/05/2026 | WBSRDA-II | 18.15 | 0 | 0 | 0
104 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Repair ofL029-L027 Uttar Hallyan to Enayetpur L029road damaged by PHE Dept. Package No. WB-09-239 |  |  | BILL/00246/2026-2027 |  | 26/05/2026 | 26/05/2026 | WBSRDA-II | 7.86 | 0 | 0 | 0
105 | HOWRAH |  | Howrah Division | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | PHE Restoration work of road from L033-T03 Lolitagari to Uttarpara L033 Gadaipur kheyag hat to Lalita gori at Hatgachha-I GP under Uluberia-I block in the district of Howrah vide Pkg no- WB-09-218 |  |  | BILL/00242/2026-2027 |  | 26/05/2026 | 26/05/2026 | WBSRDA-II | 25.18 | 0 | 0 | 0
106 | HOWRAH |  | Electrical | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | SM/19186 | Augmentation | Diesel Charges Billing month of september, 2024 |  |  | BILL/04723/2025-2026 |  | 08/12/2025 | 08/12/2025 | S.P. CONSTRUCTION | 0.11 | 0 | 0 | 0
Total | [13 empty] | 40670.19 | 414.87 | 1.02