## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Additional work in connection with commissioning of Water Treatment Plant under SANKRAIL SURFACE WATER BASED WATER SUPPLY PROJECT of Howrah District under Howrah Division, P.H.E. Dte. (TSM/019257) | AE/SADAR | JE Sadar,Junior Engineer | ORD/000067/2024-2025 | 3105/HD | 08/07/2024 | 30/03/2026 | GBC INFRASTRUCTURE PRIVATE LIMITED | 405.4 | 173.88 | 42.89 | 10
2 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Design, Construction, supply, erection and commissioning of additional fixed type intake jetty of Raw Water pipe carrying RCC walkway with all necessary components from 35 Mtr chainage of carriageway to connecting metal road of RAW WATER INTAKE near Manikpur ferry ghat on Hooghly river along with other allied works of Augmentation of surface water based Sankrail Piped Water Supply Scheme of SANKRAIL BLOCK (including Sankrail Food Park) and part of Domjur, Panchla & Uluberia-II Blocks of Howrah District under Howrah Division, PHE Dte. (SM/19187) | AE/SADAR | JE Sadar | ORD/000119/2024-2025 | 3925/HD | 09/09/2024 | 08/12/2024 | GBC INFRASTRUCTURE PRIVATE LIMITED | 2185.5 | 1623.02 | 74.26 | 10
3 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 4718/HD | 12/11/2024 | 12/11/2024 | Resource Division | 233.2 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2024-2025 | 4718/HD | 12/11/2024 | 12/11/2024 | Resource Division | 177.21 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2024-2025 | 4718/HD | 12/11/2024 | 12/11/2024 | Resource Division | 93.64 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 4718/HD | 12/11/2024 | 12/11/2024 | Resource Division | 33.48 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2024-2025 | 4718/HD | 12/11/2024 | 12/11/2024 | Resource Division | 329.84 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2024-2025 | 4718/HD | 12/11/2024 | 12/11/2024 | Resource Division | 56.03 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2024-2025 | 4718/HD | 12/11/2024 | 12/11/2024 | Resource Division | 160.35 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | 4718/HD | 12/11/2024 | 12/11/2024 | Resource Division | 240.65 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2024-2025 | 4718/HD | 12/11/2024 | 12/11/2024 | Resource Division | 113.45 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2024-2025 | 4718/HD | 12/11/2024 | 12/11/2024 | Resource Division | 98.37 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2024-2025 | 5224/HD | 13/12/2024 | 13/12/2024 | Resource Division | 3852.02 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 4718/HD | 12/11/2024 | 12/11/2024 | Resource Division | 255.11 | 0 | 0 | 0
15 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2024-2025 | 4718/HD | 12/11/2024 | 12/11/2024 | Resource Division | 93.99 | 0 | 0 | 0
16 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2024-2025 | 4718/HD | 12/11/2024 | 12/11/2024 | Resource Division | 120.02 | 0 | 0 | 0
17 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2024-2025 | 5380/HD | 26/12/2024 | 26/12/2024 | Resource Division | 124.66 | 0 | 0 | 0
18 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-6A for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 3997] | AE/SADAR | Junior Engineer | ORD/000611/2023-2024 | 1188/HD | 09/03/2024 | 01/04/2026 | M/S. GHOSH CONSTRUCTION | 750.92 | 0 | 0 | 80
19 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-7 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 6811] | AE/SADAR | Junior Engineer | ORD/000619/2023-2024 | 1189/HD | 09/03/2024 | 01/01/2026 | MAHI ENTERPRISE | 825.27 | 0 | 0 | 20
20 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Surveying, designing, laying, commissioning of two separate rising mains for conveyance of treated water from CWR at Sankrail WTP premises to 14 nos. OHRs (12 nos. new, 02 no. existing) falling under jurisdiction of PHE Dte. at Sankrail, Domjur (Part), Panchla (Part), Uluberia-II (Part) block and 09 nos. overhead reservoirs falling under jurisdiction of KMDA (erstwhile KMW&SA) at Sankrail (Part) and Domjur (Part) block and to 01 no. GLR at Sankrail Food Park. Design of foundation, construction and commissioning of foundation and superstructure of 12 nos. OHRs of different capacity, 1No. GLR, minor repair, maintenance and painting of 02 nos. existing OHRs, and other allied works along with Trial run of 3 months and 6 (six) months operation and maintenance of the entire system. | AE/SADAR |  | ORD/000606/2023-2024 | 1288/HD | 13/03/2024 | 13/03/2025 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 10463 | 40.17 | 0.38 | 2
21 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-3 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 3325] | AE/SADAR | je_how_rws_jagat,Junior Engineer | ORD/000609/2023-2024 | 1187/HD | 09/03/2024 | 01/01/2026 | M/S SARADA CONSTRUCTION | 1010.66 | 0 | 0 | 10
22 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-5 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 8336] | AE/SADAR | Junior Engineer | ORD/000610/2023-2024 | 1170/HD | 07/03/2024 | 01/01/2026 | SAMIRON GHOSH | 1396.13 | 0 | 0 | 30
23 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-10 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 7772] | AE/SADAR | Junior Engineer | ORD/000616/2023-2024 | 1192/HD | 09/03/2024 | 31/12/2025 | DEBAPRIYA DUTTA | 981.48 | 0 | 0 | 50
24 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-9B for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 5717] | AE/SADAR | JE Sadar | ORD/000615/2023-2024 | 1174/HD | 07/03/2024 | 01/07/2026 | MONDAL ENTERPISE | 947 | 0 | 0 | 30
25 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-1 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 7417] | AE/SADAR | JE Sadar,Junior Engineer | ORD/000607/2023-2024 | 1185/HD | 09/03/2024 | 01/01/2026 | THE UNICON ENGINEERS | 1192.14 | 0 | 0 | 45
26 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-2 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 5396] | AE/SADAR | JE Sadar | ORD/000608/2023-2024 | 1186/HD | 09/03/2024 | 01/10/2026 | LIMRA CONSTRUCTION AND INDUSTRIAL DEVELOPMENT | 907.2 | 0 | 0 | 30
27 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-6B for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 3997] | AE/SADAR | JE Sadar,Junior Engineer | ORD/000612/2023-2024 | 1171/HD | 07/03/2024 | 01/01/2026 | GUPTA ENTERPRISE | 589.74 | 0 | 0 | 30
28 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-11 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 8889] | AE/SADAR | JE Sadar,Junior Engineer | ORD/000617/2023-2024 | 1165/HD | 07/03/2024 | 01/07/2026 | M/S R.S. CONSTRUCTION | 1341.84 | 0 | 0 | 10
29 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-9A for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 5719] | AE/SADAR | JE Sadar | ORD/000614/2023-2024 | 1190/HD | 09/03/2024 | 01/07/2026 | MONDAL PRECISION PRIVATE LIMITED | 617.29 | 0 | 0 | 10
30 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2025-2026 | 1890/HD | 17/04/2025 | 17/04/2025 | Resource Division | 367.99 | 0 | 0 | 0
31 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Way leave facility charge for laying 1000 mm dia casing pipe with 800 mm carrier pipe along the Railway track near SANKRAIL Rail station under Augmentation of surface water based SANKRAIL piped water supply scheme.(SM /19187) |  |  | BILL/00294/2025-2026 | W/145 | 10/07/2025 | 10/07/2025 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 168.06 | 0 | 0 | 0
32 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Permanent Restoration for probable damage stretches, from Ch.0.000 Km to 3.190 Km, due to Laying pipe line along Bauria Feeder Road for LDS work in Zone-5 under Sankrail Surface project, Block-Uluberia under Howrah Highway Division in the district of Howrah. |  |  | BILL/00172/2025-2026 |  | 19/05/2025 | 19/05/2025 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 28.44 | 0 | 0 | 0
33 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Sarenga Bridge approach at Hirapur to Nalpur Station Road from 1.70 km to 2.70 km Permanent Restoration of PHE cutting for laying pipe line under Howrah Highway Division in the district of Howrah. |  |  | BILL/00171/2025-2026 |  | 19/05/2025 | 19/05/2025 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 24.96 | 0 | 0 | 0
34 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Andul feeder Road from 0.00 km to 0.300 km, permanent restoration work of PHE cutting for laying pipe line under Howrah Highway Division,P.W(Roads) Directorate in the district of Howrah during the year of 2025-26(Deposit Head) under Augmentation of surface water based Sankrail pipe water supply scheme. (SM/19187) |  |  | BILL/00475/2025-2026 |  | 12/08/2025 | 12/08/2025 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 8.07 | 0 | 0 | 0
35 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Dhulagarh domjur via begri road from 0.00 km to 1.00 km, Restoration work of PHE cutting for laying pipe line under Howrah Highway Division in the District of Howrah. under Augmentation of surface water based Sankrail pipe water supply scheme. (SM/19187) |  |  | BILL/00476/2025-2026 |  | 12/08/2025 | 12/08/2025 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 4.3 | 0 | 0 | 0
36 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-8 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 9861] | AE/SADAR | JE Sadar,Junior Engineer | ORD/000613/2023-2024 | 1172/HD | 07/03/2024 | 01/04/2026 | BALAJI UDDYOG | 915.09 | 0 | 0 | 25
37 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Laying Distribution Pipeline and providing FHTC at Zone-4 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 1810] | AE/SADAR | JE Sadar,Junior Engineer | ORD/000618/2023-2024 | 1191/HD | 09/03/2024 | 01/07/2025 | M/S SHIBAM ENTERPRISE | 763.31 | 0 | 0 | 0
38 | HOWRAH |  | Howrah Division | Augmentation of surface water based Sankrail Piped water supply scheme | SM/19187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000077/2025-2026 | 402/HD | 13/02/2026 | 13/02/2026 | Resource Division | 32.6 | 0 | 0 | 0
Total | [13 empty] | 31908.4 | 1837.08 | 5.76