## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Solarisation of WBSEDCL energised electrical installation at different PWSS in the district of Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer6 | ORD/000608/2023-2024 | 3085/ED | 17/07/2023 | 17/01/2024 | A.K. INDUSTRIES | 119.89 | 80.39 | 67.06 | 80
Total | [13 empty] | 119.89 | 80.39 | 67.06