## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Solarisation of WBSEDCL energised electrical installation at different PWSS in the district of Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer6 | ORD/000608/2023-2024 | 3085/ED | 17/07/2023 | 17/01/2024 | A.K. INDUSTRIES | 119.89 | 80.39 | 67.06 | 80
2 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Gouripur w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008708286 Consumer ID- 103301846 SM Code- 16446 |  |  | BILL/02034/2025-2026 |  | 07/08/2025 | 07/08/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
3 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Bauria w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008481242 Consumer ID- 103988694 SM Code : 16446 |  |  | BILL/01218/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 0.33 | 0 | 0 | 0
4 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Kanupat w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008688598 Consumer ID- 135073173 SM Code- 16446 |  |  | BILL/02032/2025-2026 |  | 07/08/2025 | 07/08/2025 | WBSEDCL | 0.45 | 0 | 0 | 0
5 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Deposit of application fees money for Solar Power Plant Application No- 1008132714 Consumer ID- 103286247 SM Code- 16446 |  |  | BILL/01007/2025-2026 |  | 30/05/2025 | 30/05/2025 | WBSEDCL | 0.01 | 0 | 0 | 0
6 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Hallyan w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007859351 Consumer ID- 133191636 SM Code- 16446 |  |  | BILL/02268/2025-2026 |  | 19/08/2025 | 19/08/2025 | WBSEDCL | 0.5 | 0 | 0 | 0
7 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Deposit of application fees money for Solar Power Plant Application No- 1008376696 Consumer ID- 135110959 SM Code- 16446 |  |  | BILL/01009/2025-2026 |  | 30/05/2025 | 30/05/2025 | WBSEDCL | 0.01 | 0 | 0 | 0
8 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Deposit of application fees money for Solar Power Plant Application No- 1008376628 Consumer ID- 100567011 SM Code- 16446 |  |  | BILL/01008/2025-2026 |  | 30/05/2025 | 30/05/2025 | WBSEDCL | 0.01 | 0 | 0 | 0
9 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Benapur w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007859432 Consumer ID- 101325135 SM Code- 16446 |  |  | BILL/02269/2025-2026 |  | 19/08/2025 | 19/08/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
10 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Majukhetra w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007608539 Consumer ID- 104645481 SM Code- 16446 |  |  | BILL/01010/2025-2026 |  | 30/05/2025 | 30/05/2025 | WBSEDCL | 0.31 | 0 | 0 | 0
11 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Jagannathpur w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007608590 Consumer ID- 106026058 SM Code- 16446 |  |  | BILL/01012/2025-2026 |  | 30/05/2025 | 30/05/2025 | WBSEDCL | 0.31 | 0 | 0 | 0
12 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Deposit of quotation money for solar power plant at Kashmoli w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008132714 Consumer ID- 103286247 SM Code- 16446 |  |  | BILL/03958/2025-2026 |  | 12/11/2025 | 12/11/2025 | WBSEDCL | 0.3 | 0 | 0 | 0
13 | HOWRAH |  | Electrical | Solarisation of WBSEDCL energised electrical installation at PWSS in the District of Howrah under Electrical Division, PHE, Dte. | SM/16446 | Solarisation | Deposit of application fees for Solar Power Plant Application No- 1008176341 Consumer ID- 104525267 SM Code : 16446 |  |  | BILL/01191/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 0.26 | 0 | 0 | 0
Total | [13 empty] | 122.82 | 80.39 | 65.46