## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | Assistant Engineer | Junior Engineer | ORD/000214/2024-2025 | 3201/RS | 31/12/2024 | 31/03/2025 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 85.23 | 0 | 0 | 99
2 | JHARGRAM |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | Assistant Engineer | Junior Engineer | ORD/000214/2024-2025 | 3201/RS | 31/12/2024 | 31/03/2025 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 85.23 | 0 | 0 | 99
3 | PURBA MEDINIPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | Assistant Engineer | Junior Engineer | ORD/000214/2024-2025 | 3201/RS | 31/12/2024 | 31/03/2025 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 85.23 | 0 | 0 | 99
4 | HOWRAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District for the period of 3 months from 01/01/2025 to 31/03/2025. | Assistant Engineer | Junior Engineer | ORD/000210/2024-2025 | 3200/RS | 31/12/2024 | 31/03/2025 | KARNAJORA AGNIBINA SEVA SAMITY | 62.61 | 0 | 0 | 99
5 | JHARGRAM |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District for the period of 3 months from 01/01/2025 to 31/03/2025. | Assistant Engineer | Junior Engineer | ORD/000210/2024-2025 | 3200/RS | 31/12/2024 | 31/03/2025 | KARNAJORA AGNIBINA SEVA SAMITY | 62.61 | 0 | 0 | 99
6 | PURBA MEDINIPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District for the period of 3 months from 01/01/2025 to 31/03/2025. | Assistant Engineer | Junior Engineer | ORD/000210/2024-2025 | 3200/RS | 31/12/2024 | 31/03/2025 | KARNAJORA AGNIBINA SEVA SAMITY | 62.61 | 0 | 0 | 99
7 | HOWRAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | Assistant Engineer | Junior Engineer | ORD/000361/2023-2024 | 795/RS | 11/03/2024 | 11/11/2024 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 213.67 | 181.08 | 84.75 | 50
8 | JHARGRAM |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | Assistant Engineer | Junior Engineer | ORD/000361/2023-2024 | 795/RS | 11/03/2024 | 11/11/2024 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 213.67 | 181.08 | 84.75 | 50
9 | PURBA MEDINIPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | Assistant Engineer | Junior Engineer | ORD/000361/2023-2024 | 795/RS | 11/03/2024 | 11/11/2024 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 213.67 | 181.08 | 84.75 | 50
10 | HOWRAH |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District for the period of 7(Seven) months from 01/06/2024 to 31/12/2024. | Assistant Engineer | Junior Engineer | ORD/000374/2023-2024 | 833/RS | 13/03/2024 | 13/10/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 126.46 | 107.17 | 84.75 | 50
11 | JHARGRAM |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District for the period of 7(Seven) months from 01/06/2024 to 31/12/2024. | Assistant Engineer | Junior Engineer | ORD/000374/2023-2024 | 833/RS | 13/03/2024 | 13/10/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 126.46 | 107.17 | 84.75 | 50
12 | PURBA MEDINIPUR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District for the period of 7(Seven) months from 01/06/2024 to 31/12/2024. | Assistant Engineer | Junior Engineer | ORD/000374/2023-2024 | 833/RS | 13/03/2024 | 13/10/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 126.46 | 107.17 | 84.75 | 50
13 | HOWRAH |  | Tamluk Division | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (From 03.01.2025 to 02.04.2025) | Assistant Engineer | Junior Engineer | ORD/000589/2024-2025 | 01/TD | 02/01/2025 | 02/04/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 134.21 | 0 | 0 | 100
14 | JHARGRAM |  | Tamluk Division | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (From 03.01.2025 to 02.04.2025) | Assistant Engineer | Junior Engineer | ORD/000589/2024-2025 | 01/TD | 02/01/2025 | 02/04/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 134.21 | 0 | 0 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Jhargram, Purba Medinipur , Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19238 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (From 03.01.2025 to 02.04.2025) | Assistant Engineer | Junior Engineer | ORD/000589/2024-2025 | 01/TD | 02/01/2025 | 02/04/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 134.21 | 0 | 0 | 100
Total | [13 empty] | 1866.55 | 864.75 | 46.33