## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Jhargram , Purba Medinipur, Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19354 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (For 12 months) | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 3327/TD | 27/12/2023 | 27/12/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 536.61 | 0 | 0 | 75
2 | JHARGRAM |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Jhargram , Purba Medinipur, Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19354 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (For 12 months) | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 3327/TD | 27/12/2023 | 27/12/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 536.61 | 0 | 0 | 75
3 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Jhargram , Purba Medinipur, Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19354 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (For 12 months) | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 3327/TD | 27/12/2023 | 27/12/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 536.61 | 0 | 0 | 75
4 | HOWRAH |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Jhargram , Purba Medinipur, Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19354 |  | Continuation Work Order for Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (i.e. 03.04.2025 to 02.04.2026. For 12 months) | Assistant Engineer | Junior Engineer | ORD/000658/2024-2025 | 943/TD | 27/03/2025 | 27/03/2026 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 454.76 | 0 | 0 | 75
5 | JHARGRAM |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Jhargram , Purba Medinipur, Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19354 |  | Continuation Work Order for Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (i.e. 03.04.2025 to 02.04.2026. For 12 months) | Assistant Engineer | Junior Engineer | ORD/000658/2024-2025 | 943/TD | 27/03/2025 | 27/03/2026 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 454.76 | 0 | 0 | 75
6 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Jhargram , Purba Medinipur, Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19354 |  | Continuation Work Order for Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (i.e. 03.04.2025 to 02.04.2026. For 12 months) | Assistant Engineer | Junior Engineer | ORD/000658/2024-2025 | 943/TD | 27/03/2025 | 27/03/2026 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 454.76 | 0 | 0 | 75
7 | HOWRAH |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Jhargram , Purba Medinipur, Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19354 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District for the period of 12 months from 01/04/2025 to 31/03/2026. | Assistant Engineer | Junior Engineer | ORD/000283/2024-2025 | 602/RS | 17/03/2025 | 17/03/2026 | KARNAJORA AGNIBINA SEVA SAMITY | 162.87 | 0 | 0 | 25
8 | JHARGRAM |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Jhargram , Purba Medinipur, Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19354 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District for the period of 12 months from 01/04/2025 to 31/03/2026. | Assistant Engineer | Junior Engineer | ORD/000283/2024-2025 | 602/RS | 17/03/2025 | 17/03/2026 | KARNAJORA AGNIBINA SEVA SAMITY | 162.87 | 0 | 0 | 25
9 | PURBA MEDINIPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Jhargram , Purba Medinipur, Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19354 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District for the period of 12 months from 01/04/2025 to 31/03/2026. | Assistant Engineer | Junior Engineer | ORD/000283/2024-2025 | 602/RS | 17/03/2025 | 17/03/2026 | KARNAJORA AGNIBINA SEVA SAMITY | 162.87 | 0 | 0 | 25
10 | HOWRAH |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Jhargram , Purba Medinipur, Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19354 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | Assistant Engineer | Junior Engineer | ORD/000286/2024-2025 | 597/RS | 13/03/2025 | 13/03/2026 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 257.76 | 0 | 0 | 25
11 | JHARGRAM |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Jhargram , Purba Medinipur, Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19354 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | Assistant Engineer | Junior Engineer | ORD/000286/2024-2025 | 597/RS | 13/03/2025 | 13/03/2026 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 257.76 | 0 | 0 | 25
12 | PURBA MEDINIPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Jhargram , Purba Medinipur, Howrah districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19354 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Howrah District. | Assistant Engineer | Junior Engineer | ORD/000286/2024-2025 | 597/RS | 13/03/2025 | 13/03/2026 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 257.76 | 0 | 0 | 25
Total | [13 empty] | 4235.98 | 0 | 0