## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of Chemicals & Consumables,Glassware etc. and expenditure regarding annual maintenance contract of computer,printer,UPS and other related peripherals for 15 Nos. Water Testing Laboratories | SM/06621 | Support-WQMSP | Continuation of Laboratory maintenance charges of Basanti water testing laboratories under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/002151/2019-2020 | 1456/CSD | 02/03/2020 | 02/03/2020 | SUSHANTA MANDAL | 0.7 | 0.7 | 100 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of Chemicals & Consumables,Glassware etc. and expenditure regarding annual maintenance contract of computer,printer,UPS and other related peripherals for 15 Nos. Water Testing Laboratories | SM/06621 | Support-WQMSP | Laboratories maintenance charges |  |  | VCH/002295/2021-2022 | BP-2021-22-537 | 22/03/2022 | 22/03/2022 | SOUTHERN HEALTH IMPROVEMENT SAMITY | 0.99 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of Chemicals & Consumables,Glassware etc. and expenditure regarding annual maintenance contract of computer,printer,UPS and other related peripherals for 15 Nos. Water Testing Laboratories | SM/06621 | Support-WQMSP | Remuneration of Laboratory personnel. |  |  | VCH/002299/2021-2022 | BP-2021-22-541 | 22/03/2022 | 22/03/2022 | RAMKRISHNA MISSION ASHRAMA | 0.96 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of Chemicals & Consumables,Glassware etc. and expenditure regarding annual maintenance contract of computer,printer,UPS and other related peripherals for 15 Nos. Water Testing Laboratories | SM/06621 | Support-WQMSP | Remuneration of Chemist,Bacteriologist and Lab.Assistant of Ditrict Water Testing Laboratory,South 24 Parganas situated at Bijoygarh State General Hospital Complex,Kolkata under Alipore Division, PHE Dte.for the year 2020-2021 (from 01/02/2021 to 31/01/2022). [T.No.1866/AD, 20-21] |  |  | VCH/002225/2021-2022 | BP-2021-22-505 | 22/03/2022 | 22/03/2022 | NATURAL RESOURCES CONSORTIUM | 1.66 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of Chemicals & Consumables,Glassware etc. and expenditure regarding annual maintenance contract of computer,printer,UPS and other related peripherals for 15 Nos. Water Testing Laboratories | SM/06621 | Support-WQMSP | Laboratories maintenance charges |  |  | VCH/002294/2021-2022 | BP-2021-22-536 | 22/03/2022 | 22/03/2022 | RAMKRISHNA MISSION ASHRAMA | 0.75 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of Chemicals & Consumables,Glassware etc. and expenditure regarding annual maintenance contract of computer,printer,UPS and other related peripherals for 15 Nos. Water Testing Laboratories | SM/06621 | Support-WQMSP | Laboratories maintenance charges |  |  | VCH/002298/2021-2022 | BP-2021-22-540 | 22/03/2022 | 22/03/2022 | RAMKRISHNA MISSION ASHRAMA | 0.99 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of Chemicals & Consumables,Glassware etc. and expenditure regarding annual maintenance contract of computer,printer,UPS and other related peripherals for 15 Nos. Water Testing Laboratories | SM/06621 | Support-WQMSP | Laboratories maintenance charges |  |  | VCH/002296/2021-2022 | BP-2021-22-538 | 22/03/2022 | 22/03/2022 | RAMKRISHNA MISSION ASHRAMA | 0.69 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of Chemicals & Consumables,Glassware etc. and expenditure regarding annual maintenance contract of computer,printer,UPS and other related peripherals for 15 Nos. Water Testing Laboratories | SM/06621 | Support-WQMSP | Engagement of 10(Ten) nos Lab. Personnal (Sampling Assistant and Lab. Attendent), actual travelling expenses and IEC activites to the Laboratory personnel for 07 nos Laboratories in the District. of South 24 Parganas under Alipore Division, PHE Dte.for the period from 01/10/2021 to 31/12/2021. [T.No.1245/AD, 21-22] |  |  | VCH/002224/2021-2022 | BP-2021-22-506 | 17/03/2022 | 17/03/2022 | NATURAL RESOURCES CONSORTIUM | 3.48 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of Chemicals & Consumables,Glassware etc. and expenditure regarding annual maintenance contract of computer,printer,UPS and other related peripherals for 15 Nos. Water Testing Laboratories | SM/06621 | Support-WQMSP | Bill for Laboratories personnel remuneration. |  |  | VCH/002297/2021-2022 | BP-2021-22-539 | 22/03/2022 | 22/03/2022 | PASCHIMBANGA VIGYAN MANCHA | 0.26 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of Chemicals & Consumables,Glassware etc. and expenditure regarding annual maintenance contract of computer,printer,UPS and other related peripherals for 15 Nos. Water Testing Laboratories | SM/06621 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL - GLAP application for 11 mandatory parameters and training on procedures with documentation thereof for Diamond Harbour Sub-District Water Testing Laboratory under Diamond Harbour Sub-Division of Alipore Division, P.H.E Dte. [W/O NO. 310/DHSD, DATED 08.10.21] |  |  | VCH/001204/2022-2023 | BP-2022-23-152 | 29/06/2022 | 29/06/2022 | NATURAL RESOURCES CONSORTIUM | 2.68 | 0 | 0 | 0
Total | [13 empty] | 13.15 | 0.7 | 5.34