## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramratanpur W/S Scheme includ | SM/07397 | Retrofitting | Preparation of DPR including estimate for Providing FHTC at Ramratanpur W/S Scheme (Phase-A), Koaberia W/S Scheme (Phase-A), Ramtanunagar W/S Scheme (Phase-A) & Shibkalinagar W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte.[W/O NO. 513/AD, 20.08.21, T.NO. 1755/AD, 21-22] |  |  | VCH/002608/2021-2022 | BP-2021-22-511 | 22/03/2022 | 22/03/2022 | M/S R.DUTTA & CO. | 4.7 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramratanpur W/S Scheme includ | SM/07397 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Ramratanpur Water Supply Scheme, Block - Kakdwip, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001294/2020-2021 | 2276/AD | 12/10/2020 | 12/10/2021 | SARADA CONSTRUCTION | 59.73 | 103.31 | 172.97 | 95
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramratanpur W/S Scheme includ | SM/07397 | Retrofitting | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Ramratanpur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000146/2023-2024 | 145/KSD | 30/05/2023 | 19/06/2023 | MANDAL ENTERPRISE (JOYNAGAR) | 4.63 | 4.1 | 88.64 | 89
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramratanpur W/S Scheme includ | SM/07397 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000278/2023-2024 | 3077/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramratanpur W/S Scheme includ | SM/07397 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households of different habitation for Ramratanpur Water Supply Scheme, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000593/2022-2023 | 5918/AD | 19/10/2022 | 03/11/2022 | HARIDAS DUTTA | 3.64 | 3.4 | 93.35 | 90
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramratanpur W/S Scheme includ | SM/07397 | Retrofitting | Making and fixing of permanent display board at headwork site of Ramratanpur, Suryanagar Zone - I & II, Ganeshpur Left Out area PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002147/2023-2024 | 946/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.63 | 0.16 | 24.99 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramratanpur W/S Scheme includ | SM/07397 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000837/2023-2024 | 682/AD | 30/01/2024 | 30/01/2024 | Resource Division | 6.26 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramratanpur W/S Scheme includ | SM/07397 | Retrofitting | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Alipore RWS Sub-Division, Alipore Division, P.H.E. Dte. for (WB-19G-0520) |  |  | BILL/03557/2023-2024 | BP-2023-24-1264 | 27/03/2024 | 27/03/2024 | AVIK HALDER | 1.87 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 8 (eight) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramratanpur W/S Scheme includ | SM/07397 | Retrofitting | Construction, placing and fixing of FHTC platform at every individual beneficiary etc. at Ramratanpur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000465/2024-2025 | 3425/AD | 21/08/2024 | 20/09/2024 | SARADA CONSTRUCTION | 23.6 | 0 | 0 | 100
Total | [13 empty] | 105.35 | 110.97 | 105.34